## Automation Coverage
# | Category | Method | Endpoint | Postman Status | Old Collection Status | Automation Status | Java Test Class | TestNG Suites | Program Scope | Scope Detail | Legacy / Migration | MSC Automation Notes | Remaining Work | Auth Level
1 | Health & Setup | GET | /enrollmentapi/health/liveness | PASSED |  | Done | EnrollmentPingRequestTest | smoke | In Scope (optional) | Infrastructure | New in MSC (not in legacy collection) | Not in legacy Cucumber; added in MSC TestNG smoke |  | Public
2 | Health & Setup | GET | /enrollmentapi/v1/ping | PASSED | S-Current Sprint -Done | Done | EnrollmentPingRequestTest | smoke | In Scope | Core E2E — bootstrap | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | Public
3 | Setup & Metadata | GET | /enrollmentapi/v1/certificate | PASSED |  | Done | EnrollmentCertificateRequestTest | smoke | In Scope | Core E2E — bootstrap | New in MSC (not in legacy collection) | New in MSC automation (encryption setup) |  | Public
4 | Setup & Metadata | GET | /enrollmentapi/v1/usstates | PASSED |  | Done | EnrollmentUsStatesRequestTest | smoke | In Scope | Core E2E — bootstrap | New in MSC (not in legacy collection) | New in MSC automation |  | Public / Collaborator
5 | Setup & Metadata | GET | /enrollmentapi/v1/country | PASSED |  | Done | EnrollmentCountryRequestTest | smoke | In Scope | Core E2E — bootstrap | New in MSC (not in legacy collection) | New in MSC automation |  | Public
6 | Plan Selection | GET | /enrollmentapi/v1/plans | PASSED | S-Current Sprint -Done | Done | EnrollmentPlansRequestTest | smoke | In Scope | Core E2E — bootstrap | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | Collaborator
7 | Plan Selection | GET | /enrollmentapi/v1/plans/{planId} | PASSED | S-Current Sprint -Done | Done | EnrollmentPlansRequestTest | smoke | In Scope | Core E2E — bootstrap | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | Public
8 | Content | GET | /enrollmentapi/v1/content?branding={planId}&language=en&name=enrollment | PASSED |  | Done | EnrollmentContentRequestTest | regression, integration | In Scope | Core E2E — wizard | New in MSC (not in legacy collection) | New in MSC automation (not in legacy collection) |  | Acceptance / JWT
9 | Mobile Login (Optional) | POST | /mobile1api/v1/mobilemembersession | PASSED |  | Done | MobileMemberSessionRequestTest | smoke; regression (okdirect only) | In Scope (optional) | Optional | New in MSC (not in legacy collection) | New — cross-API (Mobile1); optional Postman step |  | Public
10 | Enrollment Start | POST | /enrollmentapi/v1/enrollments/enrollmentstarted | PASSED |  | Done | EnrollmentStartedRequestTest | regression, integration | In Scope (optional) | Optional — web flow | New in MSC (not in legacy collection) | New in MSC automation; web account-owner UI only |  | Public
11 | Prospect | POST | /enrollmentapi/v1/enrollments/prospects | PASSED | D-Current Sprint -Done | Done | ProspectRequestTest | regression, integration | In Scope | Core E2E — wizard | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | Public
12 | Owner | POST | /enrollmentapi/v1/enrollments/enrollment/owner-entered | PASSED | V-Current Sprint -Done | Done | OwnerEnteredTests | regression, integration | In Scope | Core E2E — wizard | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | ENROLL_PROSPECT JWT
13 | Owner | POST | /enrollmentapi/v1/enrollments/enrollment/owner-address-entered | PASSED |  | Done | OwnerAddressEnteredRequestTest | regression, integration | In Scope | Core E2E — wizard | New in MSC (not in legacy collection) | New in MSC automation (not listed in old collection) |  | ENROLL_PROSPECT JWT
14 | Beneficiary | POST | /enrollmentapi/v1/enrollments/enrollment/beneficiary-entered | PASSED | V-Current Sprint -Done | Done | BeneficiaryEnteredTests | regression, integration | In Scope | Core E2E — wizard | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | ENROLL_PROSPECT JWT
15 | Bank & Funding | POST | /enrollmentapi/v1/verify/routingnumber | PASSED | V- Current Sprint -InProgress | Done | VerifyBankRoutingNumberRequestTest | regression, integration | In Scope | Core E2E — wizard | Legacy existed — MSC automation ahead of old status | MSC automation done; old collection still marked In Progress | Confirm Stage1 green + update Jira QA-1603 | ENROLL_PROSPECT JWT
16 | Bank & Funding | POST | /enrollmentapi/v1/enrollments/enrollment/bank-entered | PASSED | D-Current Sprint -Done | Done | BankEnteredRequestTests | regression, integration | In Scope | Core E2E — wizard | Migrated from legacy (marked Done) | Migrated from legacy; old collection marked Done |  | ENROLL_PROSPECT JWT
17 | Bank & Funding | POST | /enrollmentapi/v1/enrollments/enrollment/recurring-contribution-entered | PASSED |  | Done | RecurringContributionEnteredRequestTest | regression, integration | In Scope (optional) | Optional — AIP | New in MSC (not in legacy collection) | New in MSC automation; optional skip in Postman |  | ENROLL_PROSPECT JWT
18 | Investment | POST | /enrollmentapi/v1/enrollmentallocationfunds/get | PASSED |  | Done | AllocationFundRequestTest | regression, integration | In Scope (optional) | Optional — investment helper | New in MSC (not in legacy collection) | New in MSC automation; alternative to SQL fund lookup |  | JWT
19 | Investment | POST | /enrollmentapi/v1/enrollments/enrollment/allocations-entered | PASSED | D-Current Sprint -In Progress | Done | AllocationsEnteredRequestTests | regression, integration | In Scope | Core E2E — wizard | Legacy existed — MSC automation ahead of old status | MSC automation done; old collection marked In Progress | Confirm Stage1 green + update Jira QA-1602 | ENROLL_PROSPECT JWT
20 | Submit | POST | /enrollmentapi/v1/enrollments/enrollment/review-confirm-entered | PASSED | Not Assigned- Not started | In Progress | (pending) ReviewConfirmEnteredRequestTest | — | In Scope | Core E2E — submit (BLOCKER) | New in MSC (legacy: not assigned) | Not in legacy collection; new MSC deliverable | CODE GAP — blocks account creation; QA-1604 / QA-1810 | ENROLL_PROSPECT JWT
21 | Subsequent Enrollment | GET | /enrollmentapi/v1/subsequentenrollment/banks | Not Working - 401 |  | Reseach | — | — | Out of Scope (deferred) | Out of Scope — subsequent | New in MSC (not in legacy collection) | Postman 401; not in legacy; needs research next sprint | QA-1792 — subsequent enrollment research | ENROLL_PROSPECT JWT
22 | Subsequent Enrollment | POST | /enrollmentapi/v1/enrollments/subsequentenrollment/review-confirm-entered | Not Working - 401 |  | Reseach | — | — | Out of Scope (deferred) | Out of Scope — subsequent | New in MSC (not in legacy collection) | Postman 401; not in legacy | QA-1791 — subsequent enrollment research | Member JWT
23 | Partner Integration | POST | /enrollmentapi/v1/enrollments/submit | Not Working - 401 |  | Reseach | — | — | Out of Scope (deferred) | Out of Scope — partner (Vanguard) | New in MSC (not in legacy collection) | Partner-only; Postman 401 | QA-1808 — partner integration research | Vanguard
24 | Partner Integration | GET | /enrollmentapi/v1/upromiseaccount | Authorization Failed |  | Reseach | — | — | Out of Scope (deferred) | Out of Scope — partner | New in MSC (not in legacy collection) | Partner-only; auth failed in Postman | QA-1807 | Varies
25 | OAuth | POST | /enrollmentapi/v1/oauth/token | Not Working - 401 |  | Deferred | — | — | Out of Scope (deferred) | Out of Scope — OAuth | New in MSC (not in legacy collection) | Partner/service auth; Postman 401 | Not planned for MSC E2E | Client credentials

## Summary
Enrollment Automation Coverage Summary
Generated | 2026-08-28
Source mapping | Enrollment End Points.xlsx (Dinesh)
Repo | api-test-automation/mobile/enrollment
Total endpoints (catalog) | 25
Java automated (Done) | 19
In Progress (in scope) | 1
In Progress (Out of scope) | 4
Deferred (out of scope) | 1
Core E2E endpoints | 14/15
Optional helpers automated | 5
Blocking gap | review-confirm-entered — no Java test yet
Next sprint | Subsequent + partner flows (research)

## E2E Flow Sequence
Step | Phase | Endpoint / Action | Notes
1 | Health & Setup | GET /enrollmentapi/health/liveness | Done
|  | GET /enrollmentapi/v1/ping | Done
|  | GET /enrollmentapi/v1/certificate | Done
|  | GET /enrollmentapi/v1/usstates | Done
|  | GET /enrollmentapi/v1/country | Done
|  | GET /enrollmentapi/v1/plans | Done
|  | GET /enrollmentapi/v1/plans/{planId} | Done
|  | GET /enrollmentapi/v1/content?branding={planId}&language=en&name=enrollment | Done
2 | Mobile Login (optional) | POST /mobile1api/v1/mobilemembersession -> mobileMemberJwt (MEMBER) | Done
3 | Web Start (optional) | POST /enrollmentapi/v1/enrollments/enrollmentstarted | Done
4 | Create Prospect | POST /enrollmentapi/v1/enrollments/prospects -> jwtToken (ENROLL_PROSPECT) | Done
5 | Owner Info | POST /enrollmentapi/v1/enrollments/enrollment/owner-entered | Done
|  | POST /enrollmentapi/v1/enrollments/enrollment/owner-address-entered | Done
6 | Beneficiary | POST /enrollmentapi/v1/enrollments/enrollment/beneficiary-entered | Done
7 | Bank & Funding | POST /enrollmentapi/v1/verify/routingnumber | Done
|  | POST /enrollmentapi/v1/enrollments/enrollment/bank-entered | Done
|  | POST /enrollmentapi/v1/enrollments/enrollment/recurring-contribution-entered | Done
8 | Investments | POST /enrollmentapi/v1/enrollmentallocationfunds/get | Done
|  | POST /enrollmentapi/v1/enrollments/enrollment/allocations-entered | Done
9 | Submit | POST /enrollmentapi/v1/enrollments/enrollment/review-confirm-entered | In Progress
10 | Subsequent (add account) | GET /enrollmentapi/v1/subsequentenrollment/banks | Research
|  | POST /enrollmentapi/v1/enrollments/subsequentenrollment/review-confirm-entered | Research
11 | Partner & OAuth | POST /enrollmentapi/v1/enrollments/submit | Research
|  | GET /enrollmentapi/v1/upromiseaccount | Research
|  | POST /enrollmentapi/v1/oauth/token | Deferred