## Executive Summary
Government Savings — Automation Coverage (Rebuilt)
Assessment: July 20, 2026 ¦ Rebuild validation: July 21, 2026
Metric ID | Label | Result | Numerator | Denominator | Status | Leadership safe
M-M2-IMPL | Mobile 2 business endpoint automation (code) | 96.0% | 24 | 25 | Verified | Yes
M-M2-EXEC | Mobile 2 last documented master run | 88.0% | 22 | 25 | Stale | Conditional
M-M2-CI | Mobile 2 GitLab scheduled job | 0% | 0 | 1 | Verified gap | Yes
M-M1-IMPL | Mobile 1 endpoint automation (code) | 22.2% | 6 | 27 | Verified | Yes
M-M1-EXEC | Mobile 1 execution-verified endpoints | 3.7% | 1 | 27 | Verified | Yes
M-M1-CI | Mobile 1 GitLab scheduled job | 0% | 0 | 1 | Verified gap | Yes
M-V3-UI | V3 scoped TestNG nightly share | 86.9% | 379 | 436 | Verified | Yes
M-V2-UI | V2 UP-scoped qTest share | 36.0% | 268 | 744 | Stale | Yes
M-V3-CI | V3 GitLab scheduled job | 100% | 1 | 1 | Verified | Yes
M-META-CI | Metadataweb API GitLab job | 100% | 1 | 1 | Verified | Yes
M-GHA-M2 | GHA Dashboard vertical slice | 100% | 1 | 1 | Verified external | Yes

## Business Coverage
business_area | sub_area | metric_label | numerator | denominator | counting_unit | percent_class | implementation_status | execution_status | scheduled_status | leadership_safe_wording | confidence | evidence_path | as_of_date | notes
Unite MSC | Mobile 2 API | Automatable business endpoints implemented | 24 | 24 | business API endpoints | Verified from current denominator and repository evidence | Complete for automatable scope | Stale master run 22/25 (2026-07-14); 2 endpoints added post-sign-off | Not scheduled — QA-1405 pending | Mobile 2 automation is complete for the currently defined automatable business scope; destructive operations intentionally in smoke/module suites; recurring GitLab execution remains follow-up | High | mobile2-endpoint-current-state.csv @ cee0de9 | 2026-07-21 | Excludes mobilemembers harness endpoint from automatable scope
Unite MSC | Mobile 2 API | Documented business endpoints (incl. harness) | 24 | 25 | business API endpoints | Verified implementation estimate | 24/25 implemented | Stale execution 88% | Not scheduled | Near-complete for documented business scope; harness endpoint excluded from automation numerator by design | High | mobile2-endpoint-current-state.csv | 2026-07-21
Unite MSC | Mobile 1 API | Documented business endpoints | 6 | 27 | business API endpoints | Verified from current denominator and repository evidence | Partial — sprint expansion | 1/27 execution-verified (session) | Not scheduled | Partial coverage with expansion in progress on owner profile beneficiary and bank routing | High | mobile1-endpoint-current-state.csv @ cee0de9 | 2026-07-21
Unite MSC | Mobile Enrollment API | Bootstrap / pilot endpoints | 1 | TBD | business API endpoints | Unknown | Bootstrap smoke only | No execution evidence | Not scheduled | Pilot framework in place; endpoint inventory and automation scope not yet enumerated | Medium | mobile/enrollment/ @ cee0de9 | 2026-07-21 | Do not include in MSC combined %
Unite MSC | UniteMSC microservices | Service BDD features (aggregate) | 112 | TBD | Cucumber features | Program estimate requiring reconciliation | Substantial service-level assets | Service CI only | Per-repo GitLab pipeline | Service acceptance automation exists; not a substitute for BFF API regression | Medium | UniteMSC repos / unite-mobile2 features | 2026-07-21
Unite MSC | Application source code | JaCoCo on service repos | 13 | 13 | Java microservice repos | Verified from repository code | Generated in CI | Sonar disabled | Service build/test gate | Application line coverage separate from business automation; no coverage-delta MR gate | High | source-code-coverage-assessment.md | 2026-07-21
Unite MSC | GitHub Actions | Mobile 2 Dashboard deployment validation | 1 | 1 | validated vertical slice | Verified external | Deployment slice validated | Externally validated | Workflow not in clone | Deployment validation — not nightly business regression | Medium | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | 2026-07-21
Universal Platform | Universal Enrollment | TestNG methods in nightly inventory | 303 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Majority of current high-priority enrollment journeys automated in Modern Unite nightly | High | universal-platform-coverage/01-analysis/csv/final-workstream-summary.csv | 2026-07-01 | Do not state 95% without approved denominator
Universal Platform | IDP / Authentication | TestNG methods in nightly inventory | 56 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Near-complete automation for current documented IDP regression scope | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Withdrawals | TestNG methods in nightly inventory | 20 | TBD | TestNG test methods | Verified count | Near-complete for withdrawal regression scope | Active in GitLab nightly | scheduled_regression_job | Withdrawal domain automated in nightly; transfers adjacent (12 V2 methods) | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Entity / ABLE Entity | Implemented scenarios | 6 | TBD | business scenarios | Verified implementation estimate | Partial — 6 scenarios in repo | Not confirmed in nightly job | Unknown pipeline inclusion | Partial coverage with expansion in progress; remaining work primarily Entity and newly migrated features | High | prime-test-automation/unite/unite-entity/ | 2026-07-01 | Do not state 25% without denominator
Universal Platform | Angular lib-ui | Component tests | 22 | TBD | component tests | Verified count | Component-level only | Manual/CI on push | accountowner_build_tdd partial | Component tests — not E2E business journey coverage | Medium | universal-platform-coverage/01-analysis/07-angular-analysis.md | 2026-07-01
Universal Platform | Universal API (scoped) | Unique HTTP operations | 11 | TBD | API operations | Verified count — partial scheduling | 11 ops mapped in UP ledger | Metadataweb scheduled only | scheduled_metadataweb_stage1 | API automation exists beyond metadata; only metadataweb on GitLab schedule today | High | api-operation-mapping.csv | 2026-07-01
Universal Platform | Performance journeys | In-scope JMeter journeys | 15 | TBD | business journeys | Verified count | IDP perf scheduled; others manual | AGSUP_IDP_REGRESSION_SUITE weekdays | Partial scheduled | Performance assets exist; not all journeys on recurring schedule | Medium | performance-journey-mapping.csv | 2026-07-01
Universal Platform | Nightly inventory share (technical) | Scoped TestNG methods | 379 | 436 | TestNG methods | Verified inventory share only | Implementation in repo | Active GitLab nightly | scheduled_regression_job | Technical appendix only — inventory share not functional completeness | High | 10-reconciliation-ledger.md | 2026-07-01 | NOT leadership headline metric
Legacy Unite | High-priority member portal | Daily nightly modules | 10 | 10 | active daily suite modules | Verified from repository + historical docs | Majority of high-priority journeys automated | Jenkins nightly referenced — live run not re-verified | STAGE1-Daily-Unite-Prime-Regression (docs) | Substantial automation for core member journeys; recurring Jenkins regression referenced in platform docs | Medium | AM_Regression_Reports/docs/v2/00-v2-regression-overview.md | 2026-07-21 | ~95% core flows claim is historical doc estimate — not verified denominator
Legacy Unite | High-priority member portal | Daily test methods (approx) | 454 | TBD | TestNG/Cucumber methods | Historical estimate | 10 modules with automation | Referenced nightly | See Jenkins docs | Enrollment contributions withdrawals balance login registration UGift investment options covered in daily modules | Medium | v2/00-v2-regression-overview.md | 2026-07-21
Legacy Unite | Full V2 repository | Feature files | 1538 | TBD | Cucumber feature files | Verified from repository code | Extensive code assets | Execution varies by suite | Not on GitLab V3 schedule | Extensive existing automation requiring revalidation and governed suite activation | High | unite-test-automation feature scan | 2026-07-21
Legacy Unite | UP-scoped qTest inventory (technical) | Executed qTest cases | 268 | 744 | qTest cases | Verified inventory share only — stale | Mapped cases exist | Stale export 2026-06-29 | Jenkins/Ant legacy | Technical appendix only — not functional completeness | High | 10-reconciliation-ledger.md | 2026-06-29 | NOT leadership headline metric
Legacy Unite | CSR / management / green screens | CSR maintenance + greenscreen features | TBD | TBD | feature scenarios | Program estimate requiring reconciliation | Automation assets exist | Not in 10 daily modules | Manual / deferred suites | Automation assets exist but require revalidation synchronization and inclusion in governed nightly suite | Medium | unite/testsuite/csr/ | 2026-07-21
Back-office / Batch | Backoffice subtree | Feature files | 1062 | TBD | Cucumber features | Verified from repository code | Substantial implementation | Weekly backoffice referenced Tue/Wed | Not on V3 GitLab nightly | Back-office automation implemented; recurring inclusion requires revalidation and schedule confirmation | Medium | unite/testsuite/backoffice/ | 2026-07-21 | Kofax/feed flows in backoffice tree
ASTRO / SFRP | ASTRO UI | Feature files | 391 | TBD | Cucumber features | Verified from repository code | Substantial asset base | No verified recurring execution | ASTRO-TB-REFRESH prep only | ASTRO has substantial existing automation assets; recurring execution inactive — suites require revalidation before active regression coverage | High | astro-test-automation feature scan | 2026-07-21 | 1236 scenario count from prior scan — use features as stable unit
ASTRO / SFRP | ASTRO API | Test classes | 5 | TBD | API test classes | Verified implementation estimate | Small API module | No schedule | None | API automation footprint small; scope vs GS priority TBD | Low | api-test-automation/astro/ | 2026-07-21
COPACS | Platform scope | Automation identified | 0 | TBD | N/A | Unknown | No validated automation in reviewed repos | None | None | Scope and ownership require business discovery | Low | leadership-decision-log D-10 | 2026-07-21
Performance | IDP | Scheduled perf suite | 1 | 1 | perf regression job | Verified from KB evidence | Scripts exist | Referenced weekdays ~3 AM | AGSUP_IDP_REGRESSION_SUITE | IDP performance regression on schedule; functional gate separate | Medium | perf tracker 2026-07-02 | 2026-07-02
Performance | MSC Mobile | Perf scripts | 3 | TBD | JMX/YAML pairs | Verified manually executable | Scripts exist | Manual only | AGSUP_UNITE_MSC_ENDURANCE manual | MSC performance scripts exist; no periodic trigger confirmed | Medium | performance/mobile/unite-msc/ | 2026-07-02
Reporting / Governance | qTest manual inventory | Executed cases (V2 export) | 744 | TBD | qTest cases | Stale execution evidence | Inventory exists | 2026-06-29 snapshot | No live API | qTest data stale; row-level IDs not exported | High | v2-qtest-jenkins export | 2026-06-29
Reporting / Governance | Coverage register | Platform metrics with status labels | 11 | 11 | register rows | Verified | Register maintained | Partial live collectors | Partial | Automated harmonized register feasible; APIs blocked | High | verified-metrics-register.csv | 2026-07-21

## Coverage Matrix
gs_domain | application | automation_type | business_capability | repository | suite_or_profile | test_count_or_scope | denominator | automated_numerator | verified_pct | execution_model | gitlab | github_actions | jenkins | ci_gate_status | idp_support | environments | evidence_path | confidence | status | gap_notes
Universal Platform | V2 Unite UI | UI Cucumber TestNG | UP workstreams (Enrollment IDP ABLE Withdrawal) | unite-test-automation | Ant regression targets (stage1 daily weekly) | 268 UP-scoped qTest cases mapped | 744 executed qTest population | 268 | 36.0% inventory share | Verified manually executable; Jenkins/Ant legacy | No | No | Referenced (UNITE-TB-REFRESH) | Soft gate / manual — schedule not verified in this pass | Both paths in suites | Stage1 Stage5 TB | universal-platform-coverage/01-analysis/10-reconciliation-ledger.md | High | Verified recurring regression (legacy Jenkins) | Not requirement-level coverage; V2 total repo ~2176 scenarios / 1538 features
Universal Platform | V3 Unite UI | UI Cucumber TestNG | UP UE IDP Withdrawal (+ adjacent) | prime-test-automation | stage1-ue-regression-test + stage1-unite-regression-master | 379 scoped TestNG methods | 436 nightly TestNG population | 379 | 86.9% inventory share | Verified recurring regression | scheduled_regression_job | No | No | Hard gate on scheduled job failure (exit 1) | IDP + non-IDP suites | Stage1 (scheduled) | prime-test-automation/.gitlab-ci.yml | High | Verified recurring regression | Adjacent 57 methods (contributions CSR web reg) not in 379 subtotal
Universal Platform | V3 Unite UI | UI Cucumber | Entity platform adjacent | prime-test-automation | unite-entity module | 6 scenarios | TBD business denominator | 6 | TBD | Module suite in repo | Partial (same nightly job may not include entity) | No | No | Unknown | TBD | Stage1 | prime-test-automation/unite/unite-entity/ | Medium | Verified manually executable | Pipeline inclusion for entity module not confirmed
Traditional Unite | V2 UI full surface | UI Cucumber | All V2 frontoffice + backoffice | unite-test-automation | Full testsuite tree | 2176 scenarios (feature scan) | TBD approved business scope | TBD | TBD | Verified manually executable | No | No | Jenkins Ant targets | Manual / soft | Both | Stage1 Stage5 | unite/testsuite/ (1538 features) | Medium | Verified manually executable | Backoffice 1077 scenarios — not all in nightly subset
Traditional Unite | V2 Backoffice | UI Cucumber | Backoffice batch feeds Kofax | unite-test-automation | regression-backoffice-daily | 1077 scenarios (backoffice subtree) | TBD | 1077 | TBD | Verified manually executable | No | No | Jenkins | Manual | Non-IDP typical | Stage1 | unite/bin/build.xml + testsuite/backoffice/ | Medium | Verified manually executable | Not confirmed in GitLab nightly; separate from V3 schedule
ASTRO SFRP | ASTRO UI | UI Cucumber | ORS CAS ILS backoffice | astro-test-automation | Ant regression + daily testbed | 1236 scenarios (391 features) | TBD approved scope | TBD | TBD | Verified manually executable | No | No | ASTRO-TB-REFRESH | Manual | Both | TB1 Stage1 | astro/bin/build.xml | Medium | Automation exists — schedule unverified | Not part of V2/V3 GitLab nightly
Unite MSC | Mobile 2 API | API TestNG RestAssured | MSC BFF business endpoints | api-test-automation | mobile-ms-master-regression | 24 implemented L3+ endpoints | 25 documented business endpoints | 24 | 96.0% implemented automation | Verified in code @ cee0de9; 88% stale execution @ 7ccaf46 | No scheduled mobile job | GHA Dashboard slice validated external | No | No gate yet | okdirect + nmdirect | QC4 Stage1 | mobile2-endpoint-current-state.csv @ cee0de9 | High | Implemented — execution refresh pending | mobilemembers excluded from numerator; destructive ops smoke/module only; QA-1405 nightly
Unite MSC | Mobile 1 API | API TestNG RestAssured | MSC member session profile owner beneficiary bank | api-test-automation | mobile1-* profiles | 6 implemented endpoint identities | 27 documented business endpoints | 6 | 22.2% implemented; 3.7% execution-verified | 6 in code @ cee0de9; 1 execution-verified session | No | No | No | No | okdirect + nmdirect | QC4 Stage1 | mobile1-endpoint-current-state.csv @ cee0de9 | High | In progress — sprint 26.11 | 21 endpoints remain; 5 new endpoints need execution evidence
Unite MSC | Mobile enrollment API | API TestNG | bootstrap smoke regression | api-test-automation | mobile-ms-bootstrap smoke regression | 1 bootstrap class + suites | TBD enrollment scope | TBD | TBD | Verified manually executable | No | No | No | No | TBD | QC4 Stage1 | mobile/enrollment/ | Medium | Verified manually executable | Small footprint; not nightly scheduled
Universal Platform | JSON API metadata | API TestNG | metadata web services | api-test-automation | stage1-api-metadata-pipeline | TestNG suite | ~269 methods in universal modules (excluded from UP headline) | 11 UP-scoped ops per UP assessment | 11 | TBD operation-level | Verified recurring regression | scheduled_metadataweb_stage1 | No | No | Hard gate on job failure | TBD | Stage1 | api-test-automation/.gitlab-ci.yml | High | Verified recurring regression
Universal Platform | JSON API (account auth financial risk) | API TestNG | UP microservice APIs | api-test-automation | Per-module testng.xml | 38 test classes universal/ | TBD per service inventory | TBD | TBD | Verified manually executable | No | No | No | No | TBD | QC4 Stage1 Stage5 | api-test-automation/universal/ | Medium | Verified manually executable | Not all modules on GitLab schedule
Universal Platform | UP API operations | API RestAssured | Enrollment IDP Withdrawal ops | api-test-automation | universal modules | 11 unique HTTP operations per UP ledger | TBD full service catalog | 11 | TBD | Verified manually executable | Partial (metadataweb only scheduled) | No | No | No | TBD | Stage1 | universal-platform-coverage/01-analysis/csv/api-operation-mapping.csv | High | Verified manually executable | Denominator for full GS API surface not reconciled
ASTRO | ASTRO API | API TestNG | jsonapi-astro | api-test-automation | astro module | 5 test classes | TBD | TBD | TBD | Verified manually executable | No | No | No | No | TBD | TBD | api-test-automation/astro/ | Low | Verified manually executable | Scope vs GS priority TBD
Performance | Universal Platform | Performance JMeter Taurus | Enrollment IDP journeys | performance-test-automation | universal-platform/**/*.jmx | 15 in-scope journeys per UP ledger | 36 JMX / 53 Taurus total assets | 15 | TBD journey-level | Verified manually executable | No | No | AGSUP_IDP_REGRESSION_SUITE (scheduled weekdays) | Soft/informational perf | Both | QC4 Stage1 | mobile2-api-db-validation/docs/01-shared/unite-msc-performance-testing-tracker.md | Medium | Verified recurring regression (IDP perf only) | UP enrollment perf journeys not all scheduled
Performance | Unite MSC | Performance JMeter Taurus | MSC login core GET endpoints | performance-test-automation | mobile/unite-msc/jmeter | 6 JMX + YAML pairs | TBD MSC journey catalog | 3+ verified scripts | TBD | Verified manually executable | No | No | AGSUP_UNITE_MSC_ENDURANCE (manual) | Manual only | Non-IDP verified; IDP in progress | QC4 Stage1 | performance/mobile/unite-msc/ | Medium | Verified manually executable — not scheduled | No periodic MSC perf trigger confirmed 2026-07-02
Performance | Unite legacy | Performance JMeter | Legacy login | performance-test-automation | unite/legacy-login | 1 JMX | TBD | 1 | TBD | Verified manually executable | No | No | No | Manual | TBD | TBD | performance/unite/legacy-login/ | Low | Verified manually executable | Adjacent to MSC
Unite MSC | Microservice BDD | Service Cucumber JUnit | Per-microservice acceptance | UniteMSC 14 repos | features/*.feature | 112+ Cucumber features aggregate | TBD BFF acceptance scope | N/A | N/A | Service CI via GitLab templates | Per-repo pipeline | No | No | Build/test gate on service deploy | Both | Dev/test | unite-mobile2/src/test/resources/features/ | Medium | Verified deployment validation | Not substitute for api-test-automation BFF tests
Mobile MSC | Account owner app | Angular Karma | Micro1 mobile app unit | unite-accountowner | *.spec.ts | 120 spec files | TBD | TBD | 120 | TBD | CI on branch push | accountowner_build_tdd | No | No | Build gate not full GS regression | N/A | N/A | UniteMSC/unite-accountowner/ | Medium | Verified deployment validation
COPACS | Platform | TBD | TBD | Not identified in reviewed repos | TBD | TBD | TBD | TBD | TBD | No validated automation identified | No | No | No | None | TBD | TBD | N/A | Low | No validated automation identified | Requires scope confirmation from business owners
Government Savings | Application code coverage | JaCoCo Sonar | Service unit coverage | UniteMSC microservice repos | POM jacoco config | Service unit tests | TBD | TBD | N/A | N/A | Service pipeline | GitLab shared templates | No | No | Sonar disabled RUN_SONARQUBE false | NA | NA | unite-mobile1/pom.xml | Medium | Not a QA regression gate

## CI Jobs Gates
platform | job_or_workflow_name | repository | trigger | frequency | environment | suite_or_profile | business_scope | reports_artifacts | failure_behavior | gate_status | evidence_path | confidence | notes
GitLab | prepare | api-test-automation | Pipeline default | On push/MR | Stage1 DB props | Secure files setup | N/A | env_variables.env dotenv | Non-blocking prep | Informational | api-test-automation/.gitlab-ci.yml | High | All scheduled jobs depend on secure files
GitLab | scheduled_metadataweb_stage1 | api-test-automation | only: schedules | Nightly (~1 AM per comment — schedule ID not verified in this pass) | Stage1 | stage1-api-metadata-pipeline | Universal metadataweb API | JUnit surefire | exit non-zero on test fail | Hard gate (scheduled job) | api-test-automation/.gitlab-ci.yml | High | Only confirmed GS-related nightly in api-test-automation
GitLab | download_secure_files (include) | api-test-automation | From shared include | With prepare | N/A | N/A | N/A | secure files | Unknown | Dependency | include ascensus-gs/.../includes | Medium | Job defined in external include project
GitLab | prepare | prime-test-automation | Pipeline default | On push/MR | Stage1 | Secure files | N/A | artifacts | Prep | Informational | prime-test-automation/.gitlab-ci.yml | High
GitLab | scheduled_regression_job | prime-test-automation | only: schedules | Nightly (KB cites schedule #3961313 — not re-verified live) | Stage1 | stage1-ue-regression-test + stage1-unite-regression-master | V3 UE + Unite core UI (IDP login contributions withdrawals CSR) | JUnit both modules | exit 1 if either phase fails | Hard gate (scheduled) | prime-test-automation/.gitlab-ci.yml | High | Selenium chrome service; primary V3 GS UI nightly
GitLab | stage5_smoke_job | prime-test-automation | schedule when: manual | Manual | Stage5 | stage5-smoke profiles | V3 lightweight smoke | JUnit | Unknown | Manual smoke | prime-test-automation/.gitlab-ci.yml | High | Not recurring regression
GitLab | Per-microservice pipeline | UniteMSC (14 repos) | Push/MR | Per commit | Dev/test | Maven test + Cucumber | Service under test | Jacoco Cluecumber | Typical Maven fail blocks stage | Deployment/build gate | unite-mobile1/.gitlab-ci.yml + shared unitemsc_template.yml | Medium | Exact job names in external template not in local clone
GitLab | accountowner_build_tdd | unite-accountowner | Branch push | Per commit | N/A | Angular build | Mobile account owner app | Build logs | Build fail blocks | Build gate | unite-accountowner/devops/templates/accountowner_tdd.yaml | High | Not GS regression suite
GitHub Actions | Mobile2 Dashboard vertical slice | External deployment pipeline repo (not in audit clone) | Validated with Chaitanya | N/A | Nexus consume + dashboard profile | mobile-ms-dashboard-integration | Mobile 2 deployment validation | Nexus artifact + HTML report | N/A | N/A | Failure blocks workflow run (external) | Deployment validation — not GitLab nightly | Externally validated 2026-07
Jenkins | UNITE-TB-REFRESH | unite-test-automation | Ant build.xml reference | On demand / pre-regression | TB refresh | Testbed setup | V2 Unite | Logs | Unknown | Environment prep | unite/bin/build.xml | Medium | devjenkinsnt1:8080
Jenkins | V2 regression Ant targets | unite-test-automation | Ant CLI / Jenkins job (name not in repo) | Daily/weekly targets documented | Stage1 Stage5 | regression-frontoffice-daily regression-backoffice-daily stage1-*-regression | V2 Unite UI + backoffice | TestNG reports | Unknown | Soft/manual — job name TBD | unite/bin/build.xml | Medium | Parent automation.git GitLab CI is mock
Jenkins | ASTRO-TB-REFRESH | astro-test-automation | Ant build.xml | Pre-regression | TB1 | Testbed refresh | ASTRO | Logs | Unknown | Environment prep | astro/bin/build.xml | Medium
Jenkins | AGSUP_IDP_REGRESSION_SUITE | performance-test-automation | Build periodically | H 3 * * 1-5 (weekdays ~3 AM EDT) | Load servers | IDP Taurus YAML suite | Universal Platform IDP perf | Perf reports | Unknown | Scheduled regression (perf) | mobile2-api-db-validation/.../unite-msc-performance-testing-tracker.md | Medium | Not functional API regression
Jenkins | AGSUP_UNITE_MSC_ENDURANCE | performance-test-automation | Manual parameterized | No periodic trigger (2026-07-02) | QC4 Stage1 | unite-msc-non-idp-login-remote.yaml (+ choices) | Unite MSC perf | Optional artifacts | Unknown | Manual only | Same tracker doc | Medium | IDP YAML exists; not default job choice
Jenkins | AGSUP_ENDURANCE_THROUGHPUT | performance-test-automation | Child of IDP suite | With IDP suite | Load servers | Parameterized YAML | UP perf throughput | Perf metrics | Unknown | Child job | Same tracker doc | Medium
Jenkins | V2/V3 UI regression (historical) | unite-test-automation / prime | Referenced in demand planning imports | TBD | TBD | TBD | ~779+ combined TCs Apr 2026 claim | HTML reports | TBD | TBD — refresh required | 10_IMPORTS_RAW/confluence_exports/Demand Planning Reports/ | Low | Historical counts; not verified current

## Unresolved Verification
claim_id | claim_text | verification_status | action_required
CL-003 | Mobile 2 100% (24/24) | Rejected | Replaced — see CL-004 CL-005
CL-005 | Mobile 2 projected 96% (24/25) pending sign-off | Pending verification | QC4/Stage1 rerun + matrix refresh
CL-006 | Mobile 1 22.2% verified | Rejected | Split verified vs pending
CL-008 | Mobile 1 implemented 6/27 pending evidence | Pending verification | Sprint evidence + workbook mapping
CL-009 | GitHub Actions not implemented | Rejected | Externally validated Dashboard slice
CL-011 | V3 GitLab hard merge gate | Rejected | Reclassify scheduled hard-fail