## Executive Dashboard
business_area | sub_area | metric_label | numerator | denominator | counting_unit | percent_class | implementation_status | execution_status | scheduled_status | leadership_safe_wording | confidence | evidence_path | as_of_date | notes
Unite MSC | Mobile 2 API | Automatable business endpoints implemented | 24 | 24 | business API endpoints | Verified from current denominator and repository evidence | Complete for automatable scope | Stale master run 22/25 (2026-07-14); 2 endpoints added post-sign-off | Not scheduled — QA-1405 pending | Mobile 2 automation is complete for the currently defined automatable business scope; destructive operations intentionally in smoke/module suites; recurring GitLab execution remains follow-up | High | mobile2-endpoint-current-state.csv @ cee0de9 | 2026-07-21 | Excludes mobilemembers harness endpoint from automatable scope
Unite MSC | Mobile 2 API | Documented business endpoints (incl. harness) | 24 | 25 | business API endpoints | Verified implementation estimate | 24/25 implemented | Stale execution 88% | Not scheduled | Near-complete for documented business scope; harness endpoint excluded from automation numerator by design | High | mobile2-endpoint-current-state.csv | 2026-07-21
Unite MSC | Mobile 1 API | Documented business endpoints | 6 | 27 | business API endpoints | Verified from current denominator and repository evidence | Partial — sprint expansion | 1/27 execution-verified (session) | Not scheduled | Partial coverage with expansion in progress on owner profile beneficiary and bank routing | High | mobile1-endpoint-current-state.csv @ cee0de9 | 2026-07-21
Unite MSC | Mobile Enrollment API | Bootstrap / pilot endpoints | 1 | TBD | business API endpoints | Unknown | Bootstrap smoke only | No execution evidence | Not scheduled | Pilot framework in place; endpoint inventory and automation scope not yet enumerated | Medium | mobile/enrollment/ @ cee0de9 | 2026-07-21 | Do not include in MSC combined %
Unite MSC | UniteMSC microservices | Service BDD features (aggregate) | 112 | TBD | Cucumber features | Program estimate requiring reconciliation | Substantial service-level assets | Service CI only | Per-repo GitLab pipeline | Service acceptance automation exists; not a substitute for BFF API regression | Medium | UniteMSC repos / unite-mobile2 features | 2026-07-21
Unite MSC | Application source code | JaCoCo on service repos | 13 | 13 | Java microservice repos | Verified from repository code | Generated in CI | Sonar disabled | Service build/test gate | Application line coverage separate from business automation; no coverage-delta MR gate | High | source-code-coverage-assessment.md | 2026-07-21
Unite MSC | GitHub Actions | Mobile 2 Dashboard deployment validation | 1 | 1 | validated vertical slice | Verified external | Deployment slice validated | Externally validated | Workflow not in clone | Deployment validation — not nightly business regression | Medium | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | 2026-07-21
Universal Platform | Universal Enrollment | TestNG methods in nightly inventory | 303 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Majority of current high-priority enrollment journeys automated in Modern Unite nightly | High | universal-platform-coverage/01-analysis/csv/final-workstream-summary.csv | 2026-07-01 | Do not state 95% without approved denominator
Universal Platform | IDP / Authentication | TestNG methods in nightly inventory | 56 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Near-complete automation for current documented IDP regression scope | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Withdrawals | TestNG methods in nightly inventory | 20 | TBD | TestNG test methods | Verified count | Near-complete for withdrawal regression scope | Active in GitLab nightly | scheduled_regression_job | Withdrawal domain automated in nightly; transfers adjacent (12 V2 methods) | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Entity / ABLE Entity | Implemented scenarios | 6 | TBD | business scenarios | Verified implementation estimate | Partial — 6 scenarios in repo | Not confirmed in nightly job | Unknown pipeline inclusion | Partial coverage with expansion in progress; remaining work primarily Entity and newly migrated features | High | prime-test-automation/unite/unite-entity/ | 2026-07-01 | Do not state 25% without denominator
Universal Platform | Angular lib-ui | Component tests | 22 | TBD | component tests | Verified count | Component-level only | Manual/CI on push | accountowner_build_tdd partial | Component tests — not E2E business journey coverage | Medium | universal-platform-coverage/01-analysis/07-angular-analysis.md | 2026-07-01
Universal Platform | Universal API (scoped) | Unique HTTP operations | 11 | TBD | API operations | Verified count — partial scheduling | 11 ops mapped in UP ledger | Metadataweb scheduled only | scheduled_metadataweb_stage1 | API automation exists beyond metadata; only metadataweb on GitLab schedule today | High | api-operation-mapping.csv | 2026-07-01
Universal Platform | Performance journeys | In-scope JMeter journeys | 15 | TBD | business journeys | Verified count | IDP perf scheduled; others manual | AGSUP_IDP_REGRESSION_SUITE weekdays | Partial scheduled | Performance assets exist; not all journeys on recurring schedule | Medium | performance-journey-mapping.csv | 2026-07-01
Universal Platform | Nightly inventory share (technical) | Scoped TestNG methods | 379 | 436 | TestNG methods | Verified inventory share only | Implementation in repo | Active GitLab nightly | scheduled_regression_job | Technical appendix only — inventory share not functional completeness | High | 10-reconciliation-ledger.md | 2026-07-01 | NOT leadership headline metric
Legacy Unite | High-priority member portal | Daily nightly modules | 10 | 10 | active daily suite modules | Verified from repository + historical docs | Majority of high-priority journeys automated | Jenkins nightly referenced — live run not re-verified | STAGE1-Daily-Unite-Prime-Regression (docs) | Substantial automation for core member journeys; recurring Jenkins regression referenced in platform docs | Medium | AM_Regression_Reports/docs/v2/00-v2-regression-overview.md | 2026-07-21 | ~95% core flows claim is historical doc estimate — not verified denominator
Legacy Unite | High-priority member portal | Daily test methods (approx) | 454 | TBD | TestNG/Cucumber methods | Historical estimate | 10 modules with automation | Referenced nightly | See Jenkins docs | Enrollment contributions withdrawals balance login registration UGift investment options covered in daily modules | Medium | v2/00-v2-regression-overview.md | 2026-07-21
Legacy Unite | Full V2 repository | Feature files | 1538 | TBD | Cucumber feature files | Verified from repository code | Extensive code assets | Execution varies by suite | Not on GitLab V3 schedule | Extensive existing automation requiring revalidation and governed suite activation | High | unite-test-automation feature scan | 2026-07-21
Legacy Unite | UP-scoped qTest inventory (technical) | Executed qTest cases | 268 | 744 | qTest cases | Verified inventory share only — stale | Mapped cases exist | Stale export 2026-06-29 | Jenkins/Ant legacy | Technical appendix only — not functional completeness | High | 10-reconciliation-ledger.md | 2026-06-29 | NOT leadership headline metric
Legacy Unite | CSR / management / green screens | CSR maintenance + greenscreen features | TBD | TBD | feature scenarios | Program estimate requiring reconciliation | Automation assets exist | Not in 10 daily modules | Manual / deferred suites | Automation assets exist but require revalidation synchronization and inclusion in governed nightly suite | Medium | unite/testsuite/csr/ | 2026-07-21
Back-office / Batch | Backoffice subtree | Feature files | 1062 | TBD | Cucumber features | Verified from repository code | Substantial implementation | Weekly backoffice referenced Tue/Wed | Not on V3 GitLab nightly | Back-office automation implemented; recurring inclusion requires revalidation and schedule confirmation | Medium | unite/testsuite/backoffice/ | 2026-07-21 | Kofax/feed flows in backoffice tree
ASTRO / SFRP | ASTRO UI | Feature files | 391 | TBD | Cucumber features | Verified from repository code | Substantial asset base | No verified recurring execution | ASTRO-TB-REFRESH prep only | ASTRO has substantial existing automation assets; recurring execution inactive — suites require revalidation before active regression coverage | High | astro-test-automation feature scan | 2026-07-21 | 1236 scenario count from prior scan — use features as stable unit
ASTRO / SFRP | ASTRO API | Test classes | 5 | TBD | API test classes | Verified implementation estimate | Small API module | No schedule | None | API automation footprint small; scope vs GS priority TBD | Low | api-test-automation/astro/ | 2026-07-21
COPACS | Platform scope | Automation identified | 0 | TBD | N/A | Unknown | No validated automation in reviewed repos | None | None | Scope and ownership require business discovery | Low | leadership-decision-log D-10 | 2026-07-21
Performance | IDP | Scheduled perf suite | 1 | 1 | perf regression job | Verified from KB evidence | Scripts exist | Referenced weekdays ~3 AM | AGSUP_IDP_REGRESSION_SUITE | IDP performance regression on schedule; functional gate separate | Medium | perf tracker 2026-07-02 | 2026-07-02
Performance | MSC Mobile | Perf scripts | 3 | TBD | JMX/YAML pairs | Verified manually executable | Scripts exist | Manual only | AGSUP_UNITE_MSC_ENDURANCE manual | MSC performance scripts exist; no periodic trigger confirmed | Medium | performance/mobile/unite-msc/ | 2026-07-02
Reporting / Governance | qTest manual inventory | Executed cases (V2 export) | 744 | TBD | qTest cases | Stale execution evidence | Inventory exists | 2026-06-29 snapshot | No live API | qTest data stale; row-level IDs not exported | High | v2-qtest-jenkins export | 2026-06-29
Reporting / Governance | Coverage register | Platform metrics with status labels | 11 | 11 | register rows | Verified | Register maintained | Partial live collectors | Partial | Automated harmonized register feasible; APIs blocked | High | verified-metrics-register.csv | 2026-07-21

## Metric Definitions
# Coverage Calculation Notes
**Assessment date:** 2026-07-20
**Rebuild validated:** 2026-07-21
**Single source of truth:** `verified-metrics-register.csv`
---
## 1. Metric separation (non-negotiable)
¦ # ¦ Metric ¦ Code ¦ Measured in this assessment? ¦
¦---¦--------¦------¦------------------------------¦
¦ 1 ¦ Business automation coverage ¦ B ¦ Yes — domain-specific ¦
¦ 2 ¦ API endpoint coverage ¦ B-api ¦ Yes — MSC + UP subsets ¦
¦ 3 ¦ Execution coverage ¦ C ¦ Partial — live runs mostly TBD ¦
¦ 4 ¦ CI integration coverage ¦ D ¦ Partial ¦
¦ 5 ¦ Gate coverage ¦ E ¦ Partial — scheduled vs merge gate distinguished ¦
¦ 6 ¦ Application source-code coverage ¦ A ¦ Partial — UniteMSC JaCoCo ¦
¦ 7 ¦ Traceability completeness ¦ T ¦ Low — qTest/Jira blocked ¦
**Leadership rule:** Do not combine these into one GS percentage.
---
## 2. Verified percentages (defensible for leadership)
### Universal Platform — V3 UI (inventory share)
¦ Field ¦ Value ¦
¦-------¦------:¦
¦ Numerator ¦ 379 scoped TestNG methods ¦
¦ Denominator ¦ 436 nightly source population ¦
¦ **Result** ¦ **86.9%** ¦
¦ Timestamp ¦ 2026-07-01 SME sign-off ¦
¦ Status ¦ **Verified** ¦
¦ Not ¦ Requirement-level coverage ¦
### Universal Platform — V2 UI (inventory share)
¦ Field ¦ Value ¦
¦-------¦------:¦
¦ Numerator ¦ 268 UP-scoped qTest cases ¦
¦ Denominator ¦ 744 executed qTest population ¦
¦ **Result** ¦ **36.0%** ¦
¦ Timestamp ¦ 2026-06-29 qTest export (**Stale**) ¦
¦ Status ¦ **Verified** within export scope ¦
### Mobile 2 — API endpoint automation (**leadership baseline**)
¦ Field ¦ Value ¦
¦-------¦------:¦
¦ Numerator ¦ **22** automated business endpoints ¦
¦ Denominator ¦ **25** documented business endpoints (Dinesh workbook) ¦
¦ **Result** ¦ **88.0%** ¦
¦ Timestamp ¦ **2026-07-14** @ `7ccaf46` ¦
¦ Evidence ¦ `17-mobile2-api-automation-signoff.md` ¦
¦ Status ¦ **Verified** — retain until sign-off path completes ¦
¦ Exclusions ¦ `GET mobilemembers/{planId}/{username}` — acceptance helper
### Mobile 2 — projected (pending sign-off) — **not leadership-final**
¦ Field ¦ Value ¦
¦-------¦------:¦
¦ Numerator ¦ **24** (adds YTD + `GET mobilebanks/{id}` in code @ `cee0de9`) ¦
¦ Denominator ¦ **25** ¦
¦ **Result** ¦ **96.0%** projected ¦
¦ Timestamp ¦ 2026-07-20 code review ¦
¦ Status ¦ **Pending verification** ¦
¦ Required ¦ Matrix refresh; QC4 master rerun; Stage 1 master rerun; contribution fixture documented ¦
**Do not claim 100%** — `mobilemembers` remains excluded from automation numerator by approved sign-off scope.
### Mobile 1 — API endpoint automation
¦ Field ¦ Value ¦
¦-------¦------:¦
¦ **Verified baseline** ¦ **1 / 27 = 3.7%** (`POST mobilemembersession`) @ 2026-07-09 ¦
¦ **Implemented pending evidence** ¦ **5 additional endpoints** in code @ `cee0de9` (owner
¦ **Potential** ¦ 6/27 = 22.2% — **not verified** until workbook mapping + suite/master wiring + execution evidence ¦
¦ Status ¦ **Verified 3.7%** for leadership; sprint progress reported separately ¦
---
## 3. CI / execution metrics
¦ Metric ¦ Value ¦ Status ¦
¦--------¦-------¦--------¦
¦ Mobile 2 GitLab nightly (D) ¦ 0% scheduled ¦ **Verified gap** — QA-1405 ¦
¦ GHA Dashboard slice (D) ¦ Externally validated ¦ **Verified external** — workflow repo not in clone ¦
¦ V3 scheduled regression fail-on-error (E) ¦ Yes on scheduled run ¦ **Verified** — not MR gate ¦
---
## 4. Rejected / corrected prior claims
¦ Prior claim ¦ Correction ¦
¦-------------¦------------¦
¦ Mobile 2 **100% (24/24)** ¦ **Rejected** — used manipulated denominator ¦
¦ Mobile 1 **22.2% verified** ¦ **Rejected** — conflated code presence with verified metric ¦
¦ GitHub Actions **not implemented** ¦ **Rejected** — Dashboard slice validated externally ¦
¦ V3 **hard merge gate** ¦ **Rejected** — scheduled hard-fail only ¦
See `00-review/contradiction-resolution-ledger.md`.
---
## 5. Safe leadership statements
**Safe:**
- "Mobile 2 verified endpoint automation is **22 of 25 (88%)** per July 14 sign-off evidence."
- "Code on `main` may support **24 of 25 (96%)** — pending refreshed QC4/Stage 1 runs and formal approval."
- "Mobile 1 verified automation remains **1 of 27 (3.7%)** with additional endpoints in active sprint implementation."
- "V3 Universal Experience has a **verified GitLab scheduled regression** with **379 scoped TestNG methods** (86.9% inventory share)."
**Avoid:**
- "Government Savings has X% total coverage."
- "Mobile 2 is 100% complete."
- "GitHub Actions is not implemented."
- "GitLab nightly failures block merge requests" (without pipeline rule evidence).
---
*Regenerate DOCX/XLSX: `tools/generate_gs_assessment_deliverables.py`*

## Business Platform Coverage
business_area | sub_area | metric_label | numerator | denominator | counting_unit | percent_class | implementation_status | execution_status | scheduled_status | leadership_safe_wording | confidence | evidence_path | as_of_date | notes
Unite MSC | Mobile 2 API | Automatable business endpoints implemented | 24 | 24 | business API endpoints | Verified from current denominator and repository evidence | Complete for automatable scope | Stale master run 22/25 (2026-07-14); 2 endpoints added post-sign-off | Not scheduled — QA-1405 pending | Mobile 2 automation is complete for the currently defined automatable business scope; destructive operations intentionally in smoke/module suites; recurring GitLab execution remains follow-up | High | mobile2-endpoint-current-state.csv @ cee0de9 | 2026-07-21 | Excludes mobilemembers harness endpoint from automatable scope
Unite MSC | Mobile 2 API | Documented business endpoints (incl. harness) | 24 | 25 | business API endpoints | Verified implementation estimate | 24/25 implemented | Stale execution 88% | Not scheduled | Near-complete for documented business scope; harness endpoint excluded from automation numerator by design | High | mobile2-endpoint-current-state.csv | 2026-07-21
Unite MSC | Mobile 1 API | Documented business endpoints | 6 | 27 | business API endpoints | Verified from current denominator and repository evidence | Partial — sprint expansion | 1/27 execution-verified (session) | Not scheduled | Partial coverage with expansion in progress on owner profile beneficiary and bank routing | High | mobile1-endpoint-current-state.csv @ cee0de9 | 2026-07-21
Unite MSC | Mobile Enrollment API | Bootstrap / pilot endpoints | 1 | TBD | business API endpoints | Unknown | Bootstrap smoke only | No execution evidence | Not scheduled | Pilot framework in place; endpoint inventory and automation scope not yet enumerated | Medium | mobile/enrollment/ @ cee0de9 | 2026-07-21 | Do not include in MSC combined %
Unite MSC | UniteMSC microservices | Service BDD features (aggregate) | 112 | TBD | Cucumber features | Program estimate requiring reconciliation | Substantial service-level assets | Service CI only | Per-repo GitLab pipeline | Service acceptance automation exists; not a substitute for BFF API regression | Medium | UniteMSC repos / unite-mobile2 features | 2026-07-21
Unite MSC | Application source code | JaCoCo on service repos | 13 | 13 | Java microservice repos | Verified from repository code | Generated in CI | Sonar disabled | Service build/test gate | Application line coverage separate from business automation; no coverage-delta MR gate | High | source-code-coverage-assessment.md | 2026-07-21
Unite MSC | GitHub Actions | Mobile 2 Dashboard deployment validation | 1 | 1 | validated vertical slice | Verified external | Deployment slice validated | Externally validated | Workflow not in clone | Deployment validation — not nightly business regression | Medium | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | 2026-07-21
Universal Platform | Universal Enrollment | TestNG methods in nightly inventory | 303 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Majority of current high-priority enrollment journeys automated in Modern Unite nightly | High | universal-platform-coverage/01-analysis/csv/final-workstream-summary.csv | 2026-07-01 | Do not state 95% without approved denominator
Universal Platform | IDP / Authentication | TestNG methods in nightly inventory | 56 | TBD | TestNG test methods | Verified count — no business % denominator | Near-complete for approved regression scope | Active in GitLab nightly | scheduled_regression_job | Near-complete automation for current documented IDP regression scope | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Withdrawals | TestNG methods in nightly inventory | 20 | TBD | TestNG test methods | Verified count | Near-complete for withdrawal regression scope | Active in GitLab nightly | scheduled_regression_job | Withdrawal domain automated in nightly; transfers adjacent (12 V2 methods) | High | final-workstream-summary.csv | 2026-07-01
Universal Platform | Entity / ABLE Entity | Implemented scenarios | 6 | TBD | business scenarios | Verified implementation estimate | Partial — 6 scenarios in repo | Not confirmed in nightly job | Unknown pipeline inclusion | Partial coverage with expansion in progress; remaining work primarily Entity and newly migrated features | High | prime-test-automation/unite/unite-entity/ | 2026-07-01 | Do not state 25% without denominator
Universal Platform | Angular lib-ui | Component tests | 22 | TBD | component tests | Verified count | Component-level only | Manual/CI on push | accountowner_build_tdd partial | Component tests — not E2E business journey coverage | Medium | universal-platform-coverage/01-analysis/07-angular-analysis.md | 2026-07-01
Universal Platform | Universal API (scoped) | Unique HTTP operations | 11 | TBD | API operations | Verified count — partial scheduling | 11 ops mapped in UP ledger | Metadataweb scheduled only | scheduled_metadataweb_stage1 | API automation exists beyond metadata; only metadataweb on GitLab schedule today | High | api-operation-mapping.csv | 2026-07-01
Universal Platform | Performance journeys | In-scope JMeter journeys | 15 | TBD | business journeys | Verified count | IDP perf scheduled; others manual | AGSUP_IDP_REGRESSION_SUITE weekdays | Partial scheduled | Performance assets exist; not all journeys on recurring schedule | Medium | performance-journey-mapping.csv | 2026-07-01
Universal Platform | Nightly inventory share (technical) | Scoped TestNG methods | 379 | 436 | TestNG methods | Verified inventory share only | Implementation in repo | Active GitLab nightly | scheduled_regression_job | Technical appendix only — inventory share not functional completeness | High | 10-reconciliation-ledger.md | 2026-07-01 | NOT leadership headline metric
Legacy Unite | High-priority member portal | Daily nightly modules | 10 | 10 | active daily suite modules | Verified from repository + historical docs | Majority of high-priority journeys automated | Jenkins nightly referenced — live run not re-verified | STAGE1-Daily-Unite-Prime-Regression (docs) | Substantial automation for core member journeys; recurring Jenkins regression referenced in platform docs | Medium | AM_Regression_Reports/docs/v2/00-v2-regression-overview.md | 2026-07-21 | ~95% core flows claim is historical doc estimate — not verified denominator
Legacy Unite | High-priority member portal | Daily test methods (approx) | 454 | TBD | TestNG/Cucumber methods | Historical estimate | 10 modules with automation | Referenced nightly | See Jenkins docs | Enrollment contributions withdrawals balance login registration UGift investment options covered in daily modules | Medium | v2/00-v2-regression-overview.md | 2026-07-21
Legacy Unite | Full V2 repository | Feature files | 1538 | TBD | Cucumber feature files | Verified from repository code | Extensive code assets | Execution varies by suite | Not on GitLab V3 schedule | Extensive existing automation requiring revalidation and governed suite activation | High | unite-test-automation feature scan | 2026-07-21
Legacy Unite | UP-scoped qTest inventory (technical) | Executed qTest cases | 268 | 744 | qTest cases | Verified inventory share only — stale | Mapped cases exist | Stale export 2026-06-29 | Jenkins/Ant legacy | Technical appendix only — not functional completeness | High | 10-reconciliation-ledger.md | 2026-06-29 | NOT leadership headline metric
Legacy Unite | CSR / management / green screens | CSR maintenance + greenscreen features | TBD | TBD | feature scenarios | Program estimate requiring reconciliation | Automation assets exist | Not in 10 daily modules | Manual / deferred suites | Automation assets exist but require revalidation synchronization and inclusion in governed nightly suite | Medium | unite/testsuite/csr/ | 2026-07-21
Back-office / Batch | Backoffice subtree | Feature files | 1062 | TBD | Cucumber features | Verified from repository code | Substantial implementation | Weekly backoffice referenced Tue/Wed | Not on V3 GitLab nightly | Back-office automation implemented; recurring inclusion requires revalidation and schedule confirmation | Medium | unite/testsuite/backoffice/ | 2026-07-21 | Kofax/feed flows in backoffice tree
ASTRO / SFRP | ASTRO UI | Feature files | 391 | TBD | Cucumber features | Verified from repository code | Substantial asset base | No verified recurring execution | ASTRO-TB-REFRESH prep only | ASTRO has substantial existing automation assets; recurring execution inactive — suites require revalidation before active regression coverage | High | astro-test-automation feature scan | 2026-07-21 | 1236 scenario count from prior scan — use features as stable unit
ASTRO / SFRP | ASTRO API | Test classes | 5 | TBD | API test classes | Verified implementation estimate | Small API module | No schedule | None | API automation footprint small; scope vs GS priority TBD | Low | api-test-automation/astro/ | 2026-07-21
COPACS | Platform scope | Automation identified | 0 | TBD | N/A | Unknown | No validated automation in reviewed repos | None | None | Scope and ownership require business discovery | Low | leadership-decision-log D-10 | 2026-07-21
Performance | IDP | Scheduled perf suite | 1 | 1 | perf regression job | Verified from KB evidence | Scripts exist | Referenced weekdays ~3 AM | AGSUP_IDP_REGRESSION_SUITE | IDP performance regression on schedule; functional gate separate | Medium | perf tracker 2026-07-02 | 2026-07-02
Performance | MSC Mobile | Perf scripts | 3 | TBD | JMX/YAML pairs | Verified manually executable | Scripts exist | Manual only | AGSUP_UNITE_MSC_ENDURANCE manual | MSC performance scripts exist; no periodic trigger confirmed | Medium | performance/mobile/unite-msc/ | 2026-07-02
Reporting / Governance | qTest manual inventory | Executed cases (V2 export) | 744 | TBD | qTest cases | Stale execution evidence | Inventory exists | 2026-06-29 snapshot | No live API | qTest data stale; row-level IDs not exported | High | v2-qtest-jenkins export | 2026-06-29
Reporting / Governance | Coverage register | Platform metrics with status labels | 11 | 11 | register rows | Verified | Register maintained | Partial live collectors | Partial | Automated harmonized register feasible; APIs blocked | High | verified-metrics-register.csv | 2026-07-21

## Unite MSC Endpoints
endpoint_id | http_method | path | test_class | test_method | positive_test | negative_test | branding_support | environment_support | test_data | module_regression | smoke_suite | master_regression | deployment_validation | execution_model | implementation_status | evidence_commit | notes
M2-01 | GET | /mobile2api/v1/mobileactivity/{ext} | MobileActivityRequestTest | getMobileActivity_returnsActivitySummary | Y | N | okdirect,newyork | QC4,Stage1 | dynamic ext | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9 | master-regression-testng.xml
M2-02 | GET | /mobile2api/v1/mobiletransactionhistory/{ext} | MobileTransactionHistoryRequestTest | getMobileTransactionHistory_returnsTransactions | Y | N | okdirect,newyork | QC4,Stage1 | static ext 01 | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9 | master-regression-testng.xml
M2-03 | GET | /mobile2api/v1/investments/{ext} | MobileInvestmentRequestTest | getMobileInvestments_returnsInvestments | Y | N | okdirect,newyork | QC4,Stage1 | static ext 01 | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-04 | GET | /mobile2api/v1/mobilebanks | MobileBanksRequestTest | getMobileBanks_filterDomesticBanks_returnsBanks | Y | N | okdirect | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-05 | GET | /mobile2api/v1/mobilebanks/{id} | MobileBanksRequestTest | getMobileBankById_returnsBank | Y | N | okdirect | QC4,Stage1 | dynamic bank id | Y | N | Y | N | Implemented — master regression (added post 7ccaf46) | Implemented — execution evidence pending refresh | cee0de9 | Added Sunil QA-1386 lineage
M2-06 | POST | /mobile2api/v1/mobilebanks | MobileBanksRequestTest | postMobileBanks_addsDomesticBank_returnsBanks | Y | N | okdirect | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-07 | PUT | /mobile2api/v1/mobilebanks | MobileBanksRequestTest | putMobileBanks_updatesDomesticBank_returnsBanks | Y | N | okdirect | QC4,Stage1 | dynamic | N | Y | N | N | Implemented — smoke/targeted only (destructive) | Verified automated manually executable | cee0de9 | mobile2-smoke-testng.xml; excluded from master by design
M2-08 | DELETE | /mobile2api/v1/mobilebanks | MobileBanksRequestTest | deleteMobileBanks_deletesDomesticBank_returnsBanks | Y | N | okdirect | QC4,Stage1 | dynamic | N | Y | N | N | Implemented — smoke/targeted only (destructive) | Verified automated manually executable | cee0de9 | mobile2-smoke-testng.xml
M2-09 | GET | /mobile2api/v1/content | MobileContentRequestTest | getContent_commonSavingTips_returnsContent | Y | N | okdirect,newyork | QC4,Stage1 | query params | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-10 | GET | /mobile2api/v1/plans | MobilePlansRequestTest | getMobilePlans_returnsPlans | Y | N | okdirect,newyork | QC4,Stage1 | static | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-11 | GET | /mobile2api/v1/plans/{id} | MobilePlansRequestTest | getMobilePlanById_returnsPlan | Y | N | okdirect,newyork | QC4,Stage1 | dynamic plan id | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-12 | GET | /mobile2api/v1/mobilecontribution | MobileContributionRequestTest | getMobileContribution_returnsContributionOptions | Y | N | okdirect,newyork | QC4,Stage1 | static | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-13 | GET | /mobile2api/v1/mobilecontributioncheck | MobileContributionCheckRequestTest | getMobileContributionCheck_returnsShowContributionFlag | Y | N | okdirect,newyork | QC4,Stage1 | static | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-14 | GET | /mobile2api/v1/mobilecontribution/{ext}/{id} | MobileContributionDetailRequestTest | getMobileContributionById_returnsRecurringContribution | Y | N | okdirect,newyork | QC4,Stage1 | dynamic SQL fixture | Y | N | Y | N | Implemented — master regression; Stage1 partial | Implemented — Stage1 401 known (fixture) | cee0de9 | QC4 fixture 472560
M2-15 | POST | /mobile2api/v1/mobilecontribution | MobileContributionPostRequestTest | postMobileContribution_createsRecurringContribution | Y | N | okdirect,newyork | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-16 | PUT | /mobile2api/v1/mobilecontribution/{ext}/{id} | MobileContributionPutRequestTest | putMobileContributionById_updatesRecurringContribution | Y | N | okdirect,newyork | QC4,Stage1 | dynamic SQL fixture | Y | N | Y | N | Implemented — master regression; Stage1 partial | Implemented — Stage1 401 known (fixture) | cee0de9
M2-17 | DELETE | /mobile2api/v1/mobilecontribution/{ext}/{id} | MobileContributionDeleteRequestTest | deleteMobileContributionById_removesAutomationOwnedContribution | Y | N | okdirect | QC4 | dynamic | Y | N | N | N | Implemented — module/targeted only (destructive) | Verified automated manually executable | cee0de9 | Excluded from master by design
M2-18 | GET | /mobile2api/v1/mobiledashboard | MobileDashboardRequestTest | getMobileDashboard | Y | N | okdirect,newyork | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-19 | GET | /mobile2api/v1/mobileytdsummary/{ext} | MobileYtdSummaryRequestTest | getMobileYtdSummary_returnsYtdContributionSummary | Y | N | okdirect,newyork | QC4,Stage1 | dynamic ext | Y | Y | Y | N | Implemented — master + smoke (added post 7ccaf46) | Implemented — execution evidence pending refresh | cee0de9 | master-regression L20-29; smoke suite
M2-20 | GET | /mobile2api/v1/mobilemembers/{planId}/{username} | MobileMembersRequestTest | getMobileMembers_returnsMemberForHarness | Y | N | okdirect | QC4 | acceptance harness | N | Y | N | N | Harness test — excluded from business automation numerator | Implemented smoke-only — intentional exclusion | cee0de9 | Sign-off scope exclusion
M2-21 | GET | /mobile2api/v1/mobilebalancetrend/{ext} | MobileBalanceTrendRequestTest | getMobileBalanceTrend_returnsBalanceTrend | Y | N | okdirect,newyork | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-22 | GET | /mobile2api/v1/mobileperformance/{ext} | MobilePerformanceRequestTest | getMobilePerformance_returnsPerformance | Y | N | okdirect,newyork | QC4,Stage1 | dynamic | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-23 | GET | /mobile2api/v1/mobilestackup/{planId} | MobileStackupRequestTest | getMobileStackup_returnsStackup | Y | N | okdirect,newyork | QC4,Stage1 | branding as planId | Y | N | Y | N | Implemented — master regression (duplicate class in 2 packages) | Verified automated manually executable | cee0de9 | balancetrend + stackup packages
M2-24 | GET | /mobile2api/v1/mobileugift | MobileUgiftRequestTest | getMobileUgift_returnsUgiftPage | Y | N | okdirect,newyork | QC4,Stage1 | static | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9
M2-25 | PATCH | /mobile2api/v1/mobileugift/{ext} | MobileUgiftRequestTest | patchMobileUgift_assignsUgiftId | Y | N | okdirect,newyork | QC4,Stage1 | static ext 01 | Y | N | Y | N | Implemented — master regression | Verified automated manually executable | cee0de9

## Universal Platform
workstream | business_capability | implemented_count | counting_unit | denominator_status | implementation_status | execution_status | scheduled_status | percent_claim | percent_classification | leadership_safe_wording | confidence | evidence_path | as_of_date
Universal Enrollment | 529 enrollment journeys | 303 | TestNG methods | No approved business denominator | Near-complete for approved regression scope | Active GitLab nightly | scheduled_regression_job (UE profile) | 95%+ conversational claim | Program estimate requiring reconciliation | Majority of current high-priority enrollment journeys automated in Modern Unite nightly | High | final-workstream-summary.csv; reconciliation-ledger | 2026-07-01
IDP / Authentication | Login registration auth flows | 56 | TestNG methods | No approved business denominator | Near-complete for approved scope | Active GitLab nightly | scheduled_regression_job | 95% conversational claim | Program estimate requiring reconciliation | Near-complete automation for current documented IDP regression scope | High | final-workstream-summary.csv | 2026-07-01
IDP Web Registration (adjacent) | Web registration flows | 6 | TestNG methods | Adjacent — not in 379 scoped subtotal | Implemented | May run in extended nightly | Partial | Unknown | Verified count only | Adjacent registration coverage — not in primary nightly subtotal | High | reconciliation-ledger | 2026-07-01
Withdrawals | Member withdrawal journeys | 20 | TestNG methods | No approved business denominator | Near-complete for withdrawal scope | Active GitLab nightly | scheduled_regression_job | Unknown | Verified count only | Withdrawal domain covered in nightly; transfers adjacent | High | final-workstream-summary.csv | 2026-07-01
Contributions (adjacent) | Contribution flows | 36 | TestNG methods | Adjacent — not in 379 subtotal | Implemented | Adjacent to nightly scope | Partial | Unknown | Verified count only | Contribution automation exists — adjacent to primary nightly inventory | High | reconciliation-ledger | 2026-07-01
CSR Account Maintenance (adjacent) | CSR maintenance | 15 | TestNG methods | Adjacent | Implemented | Partial | Partial | Unknown | Verified count only | CSR maintenance scenarios exist — confirm nightly inclusion | Medium | reconciliation-ledger | 2026-07-01
Entity / ABLE Entity | Entity platform scenarios | 6 | business scenarios | Denominator not enumerated | Partial — expansion in progress | Not confirmed in nightly | Unknown pipeline inclusion | 25% conversational claim | Program estimate requiring reconciliation | Partial coverage; Entity and newly migrated features are primary expansion area | High | unite-entity module; ABLE analysis | 2026-07-01
Angular lib-ui | Shared UI components | 22 | component tests | N/A — not E2E | Component tests only | CI on relevant repos | accountowner / lib-ui | Unknown | Verified count only | Component-level tests — supplement not replace E2E | Medium | 07-angular-analysis.md | 2026-07-01
Universal API | Enrollment IDP Withdrawal operations | 11 | unique HTTP operations | Full service catalog not reconciled | Implemented in api-test-automation | Metadataweb scheduled; others manual | scheduled_metadataweb_stage1 | Unknown | Verified count only | 11 scoped API operations automated; broader universal modules await scheduling | High | api-operation-mapping.csv | 2026-07-01
Performance | Enrollment IDP Withdrawal Entity journeys | 15 | JMeter journeys | Journey catalog partial | Scripts implemented | IDP perf scheduled; UE/Entity partial | AGSUP_IDP weekdays | Unknown | Verified count only | Performance journey assets exist; recurring execution uneven | Medium | performance-journey-mapping.csv | 2026-07-01
Nightly inventory (technical appendix) | Scoped vs total nightly population | 379 | 436 | TestNG methods | Inventory denominator defined | Active | GitLab scheduled | 86.9% | Verified inventory share only | Appendix metric — inventory share not requirement coverage | High | 10-reconciliation-ledger.md | 2026-07-01
Migrated features overall | 40% conversational claim | N/A | N/A | No reconciled denominator | Expansion in progress | Mixed | GitLab nightly for core domains | 40% | Program estimate requiring reconciliation | Partial coverage with expansion in progress across Entity and newly migrated features | Low | Program knowledge — no verified denominator | 2026-07-21

## Legacy Unite
module | scope_tier | automated_code_exists | active_regression | latest_execution_evidence | high_priority_member_scope | csr_management_greenscreen_scope | status | action | confidence | evidence
Enrollment | High-priority member portal | Yes | Yes — daily module 1 | Jenkins nightly referenced (docs); not live-verified 2026-07-21 | Yes | No | Active regression referenced | Confirm Jenkins job health and qTest linkage refresh | Medium | stage1-enrollments.xml; v2/00-v2-regression-overview.md
Legacy Web Registration | High-priority member portal | Yes | Yes — daily module 2 | Jenkins nightly referenced | Yes | No | Active regression referenced | Confirm live schedule | Medium | stage1-web-registration.xml
Legacy Web Login | High-priority member portal | Yes | Yes — daily module 3 | Jenkins nightly referenced | Yes | No | Active regression referenced | Confirm live schedule | Medium | stage1-web-login.xml
Account Balance / Overview | High-priority member portal | Yes | Yes — daily module 7 | Jenkins nightly referenced | Yes | No | Active regression referenced | Confirm live schedule | Medium | stage1-acct-overview.xml
Contributions | High-priority member portal | Yes | Yes — daily module 5 | Jenkins nightly referenced | Yes | Partial CSR overlap | Active regression referenced | Longest module (~9h) — monitor stability | Medium | stage1-contributions.xml
Withdrawals | High-priority member portal | Yes | Yes — daily module 6 | Jenkins nightly referenced | Yes | Partial CSR overlap | Active regression referenced | Confirm live schedule | Medium | stage1-withdrawals.xml
Transfers | High-priority member portal | Yes | Partial — within withdrawal/adjacent suites | Not isolated in 10 daily list | Yes | No | Assets exist — suite placement varies | Map transfer scenarios to governed nightly | Low | UP ledger adjacent 12 V2 methods
UGift | High-priority member portal | Yes | Partial — plan-specific features | Not in 10 daily module list | Yes | CSR UGift features exist | Assets exist — reactivation needed | Include high-priority UGift in governed regression inventory | Medium | unite/testsuite/*/ugift/
Investment Options | High-priority member portal | Yes | Yes — daily module 9 | Jenkins nightly referenced | Yes | No | Active regression referenced | Newer module — confirm timing data | Medium | stage1-investment-options.xml
Profile / Account Maintenance | High-priority member portal | Yes | Partial — member + CSR paths | CSR module 4 active | Yes | Yes CSR | Split member vs CSR paths | Clarify member self-service vs CSR nightly scope | Medium | stage1-csr-acct-maintenance.xml; member profile features
Sardine / Fraud enrollment | High-priority member portal | Yes | Yes — daily module 8 | Jenkins nightly referenced | Yes | No | Active regression referenced | Confirm live schedule | Medium | stage1-sardine-regression.xml
Empower Plan | High-priority member portal | Yes | Yes — daily module 10 | Jenkins nightly referenced | Yes | No | Active regression referenced | Newer module — confirm timing | Medium | stage1-empower-plan.xml
CSR Account Maintenance | CSR / management | Yes | Yes — daily module 4 | Jenkins nightly referenced | Partial | Yes | Active for CSR path | Keep in nightly; traceability to qTest | Medium | stage1-csr-acct-maintenance.xml
CSR Actions | CSR / management | Yes | No — not in 10 daily modules | Stale / manual | No | Yes | Assets exist — not active nightly | Revalidate sync and add to governed suite | Medium | unite/testsuite/frontoffice/csr/
CSR Green screens | CSR / management | Yes | No — not in 10 daily modules | Stale / manual | No | Yes | Assets exist — not active nightly | Revalidation and nightly inclusion decision | Medium | unite/testsuite/csr-greenscreen/
Management screens | CSR / management | Yes | No — deferred | Unknown | No | Yes | Assets exist — deferred | Inventory and prioritize for reactivation | Low | unite/testsuite/ management paths
Case-related screens | CSR / management | Yes | No — deferred | Unknown | No | Yes | Assets exist — deferred | SME scope review | Low | Provisional
Backoffice / Batch feeds | Lower-priority operational | Yes | Weekly backoffice (docs Tue/Wed) | Referenced not live-verified | No | Yes operational | Implemented — schedule confirmation needed | Confirm weekly Jenkins backoffice jobs; Kofax/feed mapping | Medium | regression-backoffice-daily; 1062 backoffice features
Plan-specific specialty | Lower-priority operational | Yes | Specialty suites (Flywire SSgA ACH) | On demand | Partial | Partial | Assets exist — targeted execution | Maintain specialty catalog | Low | v2 overview other suites
Smoke / Release gates | Cross-cutting | Yes | Smoke + release suite families | Stage5/CAT referenced | Yes | Partial | Active for promotion paths | Align with Modern Unite smoke strategy | Medium | stage5 smoke XMLs

## Back-office and Batch
asset_type | count | includes | execution_status | evidence | next_action | owner | as_of
Backoffice feature files | 1062 | Kofax feeds batch jobs | Disabled — previously scheduled weekly | unite-test-automation backoffice subtree scan | Inventory + smoke + schedule reactivation | QA Automation | 2026-07-21

## ASTRO and SFRP
asset_type | count | execution_status | evidence | next_action | owner | as_of
UI feature files | 391 | Disabled — previously scheduled | astro-test-automation repository scan | Scope decision + smoke revalidation | QA + Program | 2026-07-21

## API Automation
gs_domain | application | automation_type | business_capability | repository | suite_or_profile | test_count_or_scope | denominator | automated_numerator | verified_pct | execution_model | gitlab | github_actions | jenkins | ci_gate_status | idp_support | environments | evidence_path | confidence | status | gap_notes
Universal Platform | V2 Unite UI | UI Cucumber TestNG | UP workstreams (Enrollment IDP ABLE Withdrawal) | unite-test-automation | Ant regression targets (stage1 daily weekly) | 268 UP-scoped qTest cases mapped | 744 executed qTest population | 268 | 36.0% inventory share | Verified manually executable; Jenkins/Ant legacy | No | No | Referenced (UNITE-TB-REFRESH) | Soft gate / manual — schedule not verified in this pass | Both paths in suites | Stage1 Stage5 TB | universal-platform-coverage/01-analysis/10-reconciliation-ledger.md | High | Verified recurring regression (legacy Jenkins) | Not requirement-level coverage; V2 total repo ~2176 scenarios / 1538 features
Universal Platform | V3 Unite UI | UI Cucumber TestNG | UP UE IDP Withdrawal (+ adjacent) | prime-test-automation | stage1-ue-regression-test + stage1-unite-regression-master | 379 scoped TestNG methods | 436 nightly TestNG population | 379 | 86.9% inventory share | Verified recurring regression | scheduled_regression_job | No | No | Hard gate on scheduled job failure (exit 1) | IDP + non-IDP suites | Stage1 (scheduled) | prime-test-automation/.gitlab-ci.yml | High | Verified recurring regression | Adjacent 57 methods (contributions CSR web reg) not in 379 subtotal
Universal Platform | V3 Unite UI | UI Cucumber | Entity platform adjacent | prime-test-automation | unite-entity module | 6 scenarios | TBD business denominator | 6 | TBD | Module suite in repo | Partial (same nightly job may not include entity) | No | No | Unknown | TBD | Stage1 | prime-test-automation/unite/unite-entity/ | Medium | Verified manually executable | Pipeline inclusion for entity module not confirmed
Traditional Unite | V2 UI full surface | UI Cucumber | All V2 frontoffice + backoffice | unite-test-automation | Full testsuite tree | 2176 scenarios (feature scan) | TBD approved business scope | TBD | TBD | Verified manually executable | No | No | Jenkins Ant targets | Manual / soft | Both | Stage1 Stage5 | unite/testsuite/ (1538 features) | Medium | Verified manually executable | Backoffice 1077 scenarios — not all in nightly subset
Traditional Unite | V2 Backoffice | UI Cucumber | Backoffice batch feeds Kofax | unite-test-automation | regression-backoffice-daily | 1077 scenarios (backoffice subtree) | TBD | 1077 | TBD | Verified manually executable | No | No | Jenkins | Manual | Non-IDP typical | Stage1 | unite/bin/build.xml + testsuite/backoffice/ | Medium | Verified manually executable | Not confirmed in GitLab nightly; separate from V3 schedule
ASTRO SFRP | ASTRO UI | UI Cucumber | ORS CAS ILS backoffice | astro-test-automation | Ant regression + daily testbed | 1236 scenarios (391 features) | TBD approved scope | TBD | TBD | Verified manually executable | No | No | ASTRO-TB-REFRESH | Manual | Both | TB1 Stage1 | astro/bin/build.xml | Medium | Automation exists — schedule unverified | Not part of V2/V3 GitLab nightly
Unite MSC | Mobile 2 API | API TestNG RestAssured | MSC BFF business endpoints | api-test-automation | mobile-ms-master-regression | 24 implemented L3+ endpoints | 25 documented business endpoints | 24 | 96.0% implemented automation | Verified in code @ cee0de9; 88% stale execution @ 7ccaf46 | No scheduled mobile job | GHA Dashboard slice validated external | No | No gate yet | okdirect + nmdirect | QC4 Stage1 | mobile2-endpoint-current-state.csv @ cee0de9 | High | Implemented — execution refresh pending | mobilemembers excluded from numerator; destructive ops smoke/module only; QA-1405 nightly
Unite MSC | Mobile 1 API | API TestNG RestAssured | MSC member session profile owner beneficiary bank | api-test-automation | mobile1-* profiles | 6 implemented endpoint identities | 27 documented business endpoints | 6 | 22.2% implemented; 3.7% execution-verified | 6 in code @ cee0de9; 1 execution-verified session | No | No | No | No | okdirect + nmdirect | QC4 Stage1 | mobile1-endpoint-current-state.csv @ cee0de9 | High | In progress — sprint 26.11 | 21 endpoints remain; 5 new endpoints need execution evidence
Unite MSC | Mobile enrollment API | API TestNG | bootstrap smoke regression | api-test-automation | mobile-ms-bootstrap smoke regression | 1 bootstrap class + suites | TBD enrollment scope | TBD | TBD | Verified manually executable | No | No | No | No | TBD | QC4 Stage1 | mobile/enrollment/ | Medium | Verified manually executable | Small footprint; not nightly scheduled
Universal Platform | JSON API metadata | API TestNG | metadata web services | api-test-automation | stage1-api-metadata-pipeline | TestNG suite | ~269 methods in universal modules (excluded from UP headline) | 11 UP-scoped ops per UP assessment | 11 | TBD operation-level | Verified recurring regression | scheduled_metadataweb_stage1 | No | No | Hard gate on job failure | TBD | Stage1 | api-test-automation/.gitlab-ci.yml | High | Verified recurring regression
Universal Platform | JSON API (account auth financial risk) | API TestNG | UP microservice APIs | api-test-automation | Per-module testng.xml | 38 test classes universal/ | TBD per service inventory | TBD | TBD | Verified manually executable | No | No | No | No | TBD | QC4 Stage1 Stage5 | api-test-automation/universal/ | Medium | Verified manually executable | Not all modules on GitLab schedule
Universal Platform | UP API operations | API RestAssured | Enrollment IDP Withdrawal ops | api-test-automation | universal modules | 11 unique HTTP operations per UP ledger | TBD full service catalog | 11 | TBD | Verified manually executable | Partial (metadataweb only scheduled) | No | No | No | TBD | Stage1 | universal-platform-coverage/01-analysis/csv/api-operation-mapping.csv | High | Verified manually executable | Denominator for full GS API surface not reconciled
ASTRO | ASTRO API | API TestNG | jsonapi-astro | api-test-automation | astro module | 5 test classes | TBD | TBD | TBD | Verified manually executable | No | No | No | No | TBD | TBD | api-test-automation/astro/ | Low | Verified manually executable | Scope vs GS priority TBD
Performance | Universal Platform | Performance JMeter Taurus | Enrollment IDP journeys | performance-test-automation | universal-platform/**/*.jmx | 15 in-scope journeys per UP ledger | 36 JMX / 53 Taurus total assets | 15 | TBD journey-level | Verified manually executable | No | No | AGSUP_IDP_REGRESSION_SUITE (scheduled weekdays) | Soft/informational perf | Both | QC4 Stage1 | mobile2-api-db-validation/docs/01-shared/unite-msc-performance-testing-tracker.md | Medium | Verified recurring regression (IDP perf only) | UP enrollment perf journeys not all scheduled
Performance | Unite MSC | Performance JMeter Taurus | MSC login core GET endpoints | performance-test-automation | mobile/unite-msc/jmeter | 6 JMX + YAML pairs | TBD MSC journey catalog | 3+ verified scripts | TBD | Verified manually executable | No | No | AGSUP_UNITE_MSC_ENDURANCE (manual) | Manual only | Non-IDP verified; IDP in progress | QC4 Stage1 | performance/mobile/unite-msc/ | Medium | Verified manually executable — not scheduled | No periodic MSC perf trigger confirmed 2026-07-02
Performance | Unite legacy | Performance JMeter | Legacy login | performance-test-automation | unite/legacy-login | 1 JMX | TBD | 1 | TBD | Verified manually executable | No | No | No | Manual | TBD | TBD | performance/unite/legacy-login/ | Low | Verified manually executable | Adjacent to MSC
Unite MSC | Microservice BDD | Service Cucumber JUnit | Per-microservice acceptance | UniteMSC 14 repos | features/*.feature | 112+ Cucumber features aggregate | TBD BFF acceptance scope | N/A | N/A | Service CI via GitLab templates | Per-repo pipeline | No | No | Build/test gate on service deploy | Both | Dev/test | unite-mobile2/src/test/resources/features/ | Medium | Verified deployment validation | Not substitute for api-test-automation BFF tests
Mobile MSC | Account owner app | Angular Karma | Micro1 mobile app unit | unite-accountowner | *.spec.ts | 120 spec files | TBD | TBD | 120 | TBD | CI on branch push | accountowner_build_tdd | No | No | Build gate not full GS regression | N/A | N/A | UniteMSC/unite-accountowner/ | Medium | Verified deployment validation
COPACS | Platform | TBD | TBD | Not identified in reviewed repos | TBD | TBD | TBD | TBD | TBD | No validated automation identified | No | No | No | None | TBD | TBD | N/A | Low | No validated automation identified | Requires scope confirmation from business owners
Government Savings | Application code coverage | JaCoCo Sonar | Service unit coverage | UniteMSC microservice repos | POM jacoco config | Service unit tests | TBD | TBD | N/A | N/A | Service pipeline | GitLab shared templates | No | No | Sonar disabled RUN_SONARQUBE false | NA | NA | unite-mobile1/pom.xml | Medium | Not a QA regression gate

## Performance
asset_id | gs_domain | application | automation_type | repository | path_or_suite | test_count_unit | count | denominator_source | auth_idp | auth_non_idp | environment | execution_status | ci_integration | last_evidence_date | confidence | notes
AST-001 | Universal Platform | V2 UI | Feature scenarios | unite-test-automation | unite/testsuite/**/*.feature | Scenario lines | 2176 | TBD GS business scope | Partial | Partial | Stage1 Stage5 | Verified manually executable | Jenkins/Ant not GitLab | 2026-07-20 | Medium | Full V2 surface; nightly subset smaller
AST-002 | Universal Platform | V2 UI UP-scoped | qTest mapped cases | unite-test-automation | KP UP mapping | Executed qTest cases | 268 | 744 qTest population (UP ledger) | Partial | Partial | Stage1 | Verified manually executable | Jenkins legacy | 2026-07-01 | High | SME-reviewed UP assessment
AST-003 | Universal Platform | V3 UI | TestNG methods nightly | prime-test-automation | unite UE + unite masters | TestNG methods | 436 source / 379 scoped | 436 nightly population | Yes | Yes | Stage1 | Verified recurring regression | GitLab scheduled_regression_job | 2026-07-20 | High | 86.9% inventory share scoped
AST-004 | Universal Platform | V3 UI adjacent | TestNG methods | prime-test-automation | Contributions CSR WebReg | TestNG methods | 57 | Adjacent not in 379 | Yes | Yes | Stage1 | Verified manually executable | May overlap nightly | 2026-07-01 | Medium
AST-005 | Traditional Unite | V2 Backoffice | Feature scenarios | unite-test-automation | unite/testsuite/backoffice | Scenario lines | 1077 | TBD | Partial | Partial | Stage1 | Verified manually executable | Ant daily target exists | 2026-07-20 | Medium | Not confirmed in V3 GitLab schedule
AST-006 | ASTRO | ASTRO UI | Feature scenarios | astro-test-automation | astro/testsuite | Scenario lines | 1236 | TBD | Partial | Partial | TB1 Stage1 | Verified manually executable | Jenkins refresh only | 2026-07-20 | Medium | Not in recurring V2/V3 GitLab nightly
AST-007 | Unite MSC | Mobile 2 API | TestNG classes | api-test-automation | mobile/mobile2 | Test classes | 20 | N/A | Yes | Yes | QC4 Stage1 | Verified manually executable | Not scheduled GitLab | 2026-07-20 | High | 25 suite XMLs 30 Maven profiles
AST-008 | Unite MSC | Mobile 2 API | Endpoint L3+ tests | api-test-automation | mobile/mobile2 *RequestTest | Endpoints | 24 | 25 Dinesh excl mobilemembers | Yes | Yes | QC4 Stage1 | Verified manually executable | Pending QA-1405 | 2026-07-20 | High | 100% in-scope endpoint automation
AST-009 | Unite MSC | Mobile 2 API | Banks smoke PUT DELETE | api-test-automation | banks-smoke-testng.xml | Functional tests | 2 | N/A | No | Yes okdirect | QC4 | Verified manually executable | Smoke only | 2026-07-20 | High | Excluded from master by design
AST-010 | Unite MSC | Mobile 1 API | TestNG classes | api-test-automation | mobile/mobile1 | Test classes | 6 | 27 business endpoints | Yes | Yes | QC4 Stage1 | Verified manually executable | Not scheduled | 2026-07-20 | High | 22.2% endpoint coverage
AST-011 | Unite MSC | Mobile 1 API | Auth session | api-test-automation | Mobile1AuthenticationTest | Endpoints | 1 | 27 | Yes | Yes | QC4 Stage1 | Verified manually executable | Shared dependency for M2 | 2026-07-20 | High
AST-012 | Universal Platform | Metadata API | TestNG | api-test-automation | jsonapi-metadataweb | Suite XML | 13 suites | TBD | Partial | TBD | Stage1 | Verified recurring regression | scheduled_metadataweb_stage1 | 2026-07-20 | High
AST-013 | Universal Platform | Account Auth Financial Risk API | TestNG | api-test-automation | universal/* | Test classes | 38 | TBD | TBD | TBD | QC4 Stage1 | Verified manually executable | Not on schedule | 2026-07-20 | Medium
AST-014 | Universal Platform | UP API ops | HTTP operations | api-test-automation | universal modules | Unique operations | 11 | UP operation catalog | TBD | TBD | Stage1 | Verified manually executable | Partial CI | 2026-07-01 | High
AST-015 | Performance | UP IDP | JMeter Taurus | performance-test-automation | universal-platform/idp | Scripts | 6+ IDP journeys | TBD | Yes | No | QC4 Stage1 | Verified recurring regression | AGSUP_IDP_REGRESSION_SUITE | 2026-07-02 | Medium | Perf not functional pass/fail gate
AST-016 | Performance | Unite MSC | JMeter Taurus | performance-test-automation | mobile/unite-msc/jmeter | JMX plans | 6 | TBD MSC catalog | Partial | Yes | QC4 Stage1 | Verified manually executable | AGSUP_UNITE_MSC manual | 2026-07-02 | Medium
AST-017 | Performance | UP enrollment | JMeter | performance-test-automation | universal-platform/universal-enrollment | JMX | 7+ per UP ledger | 15 journey denominator | Partial | Partial | TBD | Verified manually executable | Not all scheduled | 2026-07-01 | Medium
AST-018 | Unite MSC | Service BDD | Cucumber features | UniteMSC 14 repos | src/test/resources/features | Features | 112 aggregate | TBD | N/A | N/A | Service CI | Verified deployment validation | Per-repo GitLab | 2026-07-20 | Medium | Not BFF acceptance layer
AST-019 | Unite MSC | Enrollment bootstrap | TestNG | api-test-automation | mobile/enrollment | Bootstrap tests | 1 class | TBD | TBD | TBD | QC4 | Verified manually executable | None | 2026-07-20 | Low
AST-020 | ASTRO | API astro module | TestNG | api-test-automation | astro/jsonapi-astro | Test classes | 5 | TBD | TBD | TBD | TBD | Verified manually executable | None | 2026-07-20 | Low

## Pipeline and CI
platform | job_name | repository | branch | commit | schedule_status | environment | gate_type | evidence | as_of | owner | notes
GitLab | scheduled_regression_job | prime-test-automation | main | 93f8628 | Active — scheduled | Stage 1 | Scheduled hard-fail | https://gitlab.com/ascensus-gs/products/depot/qa-automation/prime-test-automation/-/blob/main/.gitlab-ci.yml @ 93f8628 | 2026-07-21 | QA Automation | Modern Unite UI nightly
GitLab | scheduled_metadataweb_stage1 | api-test-automation | main | cee0de9 | Active — scheduled | Stage 1 | Scheduled hard-fail | https://gitlab.com/ascensus-gs/products/depot/qa-automation/api-test-automation/-/blob/main/.gitlab-ci.yml @ cee0de9 | 2026-07-21 | QA Automation | Metadata API nightly
GitLab | scheduled_mobile2_stage1 (QA-1405) | api-test-automation | main | cee0de9 | Pending — DevOps capacity | Stage 1 | Planned scheduled regression | Jira QA-1405; YAML absent | 2026-07-21 | DevOps + QA | Not QC4 nightly
GitHub Actions | Mobile 2 QC4 integration workflow | External workflow repo | N/A | N/A | Deployment/integration validation | QC4 | Build-deploy-test-promote | SME confirmed — Chaitanya validation; Nexus publish/consume | 2026-07-21 | DevOps + QA | Not GitLab nightly
Jenkins | STAGE1-Daily-Unite-Prime-Regression | unite-test-automation | main | 14e3b62a | Referenced — live verification pending | Stage 1 | Legacy daily regression | Platform documentation; Live verification unavailable as of 2026-07-21 | 2026-07-21 | QA Automation | 10 daily modules
Jenkins | Weekly backoffice regression | unite-test-automation | main | 14e3b62a | Disabled | Stage 1 | Previously scheduled | SME confirmed — live verification pending | 2026-07-21 | QA Automation | Kofax feeds batch
Jenkins | ASTRO regression | astro-test-automation | main | N/A | Disabled | TB1 | Previously scheduled | SME confirmed — live verification pending | 2026-07-21 | QA + Program | Reactivation required
Jenkins | AGSUP_IDP_REGRESSION_SUITE | performance-test-automation | main | N/A | Active — weekdays | Load | Performance regression | Performance tracker 2026-07-02 | 2026-07-21 | QA Performance | Not functional gate

## Source-Code Coverage
repository | platform | unit_tests_run_on_mr_pr | security_checks | code_coverage_generated | coverage_report_published | minimum_threshold_defined | coverage_regression_comparison | merge_blocked_on_coverage_failure | deployment_blocked_on_failure | authorized_bypass_available | bypass_evidence_audit_trail | current_status | evidence | owner | recommended_action
unite-mobile2 | GitLab (UniteMSC template) | Yes (service CI) | SAST via shared template; Snyk org standard | Yes JaCoCo | CI report stage (template) | Yes 90% instruction (POM jacoco-check) | No branch-vs-main delta | No verified MR coverage gate | Service deploy pipeline (template) | General MR approval bypass only | No coverage-specific waiver trail | Verified from repository code | unite-mobile2/pom.xml @ c9c2c28; .gitlab-ci.yml | Pilot coverage-delta gate Phase 1 informational
unite-mobile1 | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum (POM) | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-mobile1/pom.xml @ bfb51aa | Align threshold after pilot learnings
unite-profile | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 90% instruction | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-profile/pom.xml | Phase 2 rollout candidate
unite-account | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 50% instruction | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-account/pom.xml | Phase 2 rollout
unite-auth | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-auth/pom.xml | Introduce threshold gradually
unite-bank | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-bank/pom.xml | Introduce threshold gradually
unite-transaction | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-transaction/pom.xml | Introduce threshold gradually
unite-metadata | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-metadata/pom.xml | Introduce threshold gradually
unite-security | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-security/pom.xml | Introduce threshold gradually
unite-financial | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Properties 80% but check uses 0% | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-financial/pom.xml | Reconcile POM properties vs jacoco-check
unite-enrollment | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | unite-enrollment/pom.xml | Introduce threshold gradually
fees | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% via properties | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | fees/pom.xml | Introduce threshold gradually
util-ssnservice | GitLab (UniteMSC template) | Yes | SAST; Snyk org standard | Yes JaCoCo | CI report stage | Yes 0% minimum | No | No | Template deploy gate | General approval only | No coverage waiver | Verified from repository code | util-ssnservice/pom.xml | Introduce threshold gradually
unite-accountowner | GitLab (Angular) | Yes TDD build job | SAST Fortify template | No JaCoCo (Angular build) | No | No | No | No | Build job fail only | General approval only | No coverage waiver | Verified from repository code | accountowner_tdd.yaml @ main | Evaluate Istanbul/lcov if gate needed
api-test-automation | GitLab | MR pipeline via shared includes | Org Snyk standard | No application coverage | No coverage_report | JaCoCo on jsonapi libs only (95% lib unit tests) | No | No | No | N/A | N/A | Verified from repository code | .gitlab-ci.yml @ cee0de9; scheduled metadataweb only | Add business regression schedule QA-1405; not code-coverage gate
prime-test-automation | GitLab | MR pipeline via shared includes | Org Snyk standard | No application coverage | No coverage_report | JaCoCo on prime libs only | No | No | No | N/A | N/A | Verified from repository code | .gitlab-ci.yml @ 93f8628; scheduled V3 regression | Retain scheduled gate; separate from JaCoCo
unite-test-automation | GitLab/Jenkins | Not on GitLab MR (Automation monorepo) | Unknown | No | No | No | No | No | Jenkins Ant inferred | Unknown | Unknown | Verified from repository code | Automation @ 14e3b62a | Inventory + Jenkins collector
astro-test-automation | Jenkins | No GitLab CI in KB clone | Unknown | No | No | No | No | No | Jenkins ASTRO-TB-REFRESH | Unknown | Unknown | Verified from repository code | astro/bin/build.xml | Confirm Jenkins job scope live
performance-test-automation | Jenkins | Manual/scheduled perf | Unknown | No | No | No | No | No | Perf job fail | Unknown | Unknown | Verified from repository code | AGSUP_IDP_REGRESSION_SUITE docs | Perf gate separate from code coverage
automation-shared-resource | GitLab | Includes only | Org standard | No | No | No | No | No | N/A | N/A | N/A | Verified from repository code | .gitlab-ci.yml | No action
GitHub Actions Mobile2 workflow | GitHub Actions | Deployment validation slice | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Deployment validation | Unknown | Unknown | Verified external | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | Clone workflow repo for audit
All ascensus-gs GitLab repos | GitLab | MR pipeline required (org standard) | Snyk + SAST where configured | N/A | N/A | N/A | No verified org-wide coverage delta | No verified coverage MR block | N/A | Senior Code Review bypass (general) | No coverage exception register | Pending live verification | Org protected-branch policy; API 401 blocked | DevOps | Add coverage check as new required status

## Coverage Gates
# CI Gate Assessment — Government Savings Automation
**Assessment date:** 2026-07-20
**Platforms reviewed:** GitLab (local YAML + includes), Jenkins (doc/code references), GitHub Actions (repo scan)
---
## Executive snapshot
¦ Platform ¦ GS-related recurring jobs verified ¦ Hard gates ¦ Informational / manual ¦
¦----------¦-----------------------------------¦------------¦------------------------¦
¦ **GitLab** ¦ 2 families: V3 UI nightly + metadataweb API nightly ¦ Scheduled hard-fail on run ¦ `prepare`, manual Stage5 smoke ¦
¦ **GitHub Actions** ¦ Mobile 2 Dashboard vertical slice (external) ¦ Deployment validation ¦ Module expansion in progress ¦
¦ **Jenkins** ¦ IDP perf suite scheduled; V2/Astro via Ant references ¦ TBD — functional UI gate not confirmed ¦ MSC perf manual; TB refresh jobs ¦
---
## GitLab — verified jobs
### 1. `prime-test-automation` → `scheduled_regression_job`
¦ Attribute ¦ Detail ¦
¦-----------¦--------¦
¦ **Trigger** ¦ `only: schedules` ¦
¦ **Environment** ¦ Stage 1 ¦
¦ **Suites** ¦ `stage1-ue-regression-test` + `stage1-unite-regression-master` ¦
¦ **Technology** ¦ Selenium + Cucumber/TestNG ¦
¦ **Scope** ¦ V3 Universal Enrollment + Unite core (IDP login, contributions, withdrawals, CSR, etc.) ¦
¦ **Failure behavior** ¦ `set +e` tracks failures; **exit 1** if either Maven phase fails ¦
¦ **Gate status** ¦ **Scheduled regression — hard-fail on run** (not verified MR/deployment gate) ¦
¦ **Artifacts** ¦ JUnit from both surefire directories ¦
¦ **Evidence** ¦ `prime-test-automation/.gitlab-ci.yml` L23–80 ¦
¦ **Schedule** ¦ KB references pipeline schedule #3961313 — **live schedule not re-verified in this pass** ¦
### 2. `api-test-automation` → `scheduled_metadataweb_stage1`
¦ Attribute ¦ Detail ¦
¦-----------¦--------¦
¦ **Trigger** ¦ `only: schedules` ¦
¦ **Environment** ¦ Stage 1 ¦
¦ **Suite** ¦ `stage1-api-metadata-pipeline` on `jsonapi-metadataweb` ¦
¦ **Failure behavior** ¦ Maven test failure fails job ¦
¦ **Gate status** ¦ **Hard gate** (scheduled) ¦
¦ **Evidence** ¦ `api-test-automation/.gitlab-ci.yml` L21–51 ¦
¦ **Gap** ¦ Mobile 1/2, accountweb, auth, enrollment **not** on this schedule ¦
### 3. `api-test-automation` — Mobile 2 nightly (planned)
¦ Attribute ¦ Detail ¦
¦-----------¦--------¦
¦ **Status** ¦ **Not implemented** in local `.gitlab-ci.yml` ¦
¦ **Story** ¦ QA-1405 ¦
¦ **Spec** ¦ `api-test-automation/mobile/project-documents/18-MOBILE2-VERIFICATION-AND-MAPPING-RUNBOOK.md` ¦
¦ **Gate status** ¦ **Planned** ¦
### 4. UniteMSC microservice repos
¦ Attribute ¦ Detail ¦
¦-----------¦--------¦
¦ **Pattern** ¦ Shared `unitemsc_template.yml` include ¦
¦ **Local visibility** ¦ Stages: build → test → deploy; exact gate rules in external template ¦
¦ **Gate status** ¦ **Service build/deploy gate** — not GS E2E regression ¦
¦ **Evidence** ¦ `unite-mobile1/.gitlab-ci.yml` ¦
---
## GitHub Actions
¦ Finding ¦ Evidence ¦
¦---------¦----------¦
¦ No `.github/workflows/` in `api-test-automation` clone ¦ Directory absent in audited repo ¦
¦ Mobile 2 Nexus + Dashboard vertical slice ¦ Documented in `17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md` ¦
¦ **Dashboard slice validated with Chaitanya** ¦ Leadership pack 2026-07-17; Nexus publish/consume flow ¦
¦ Workflow repository ¦ **Not available in this audit clone** — externally validated ¦
¦ **Conclusion** ¦ **Deployment validation path exists** — separate from GitLab nightly regression; module expansion in progress ¦
---
## Jenkins
¦ Job ¦ Scope ¦ Schedule ¦ Gate? ¦ Evidence ¦
¦-----¦-------¦----------¦-------¦----------¦
¦ `AGSUP_IDP_REGRESSION_SUITE` ¦ UP IDP performance ¦ Weekdays ~3 AM ¦ Perf regression — not functional API/UI gate ¦ perf tracker 2026-07-02 ¦
¦ `AGSUP_UNITE_MSC_ENDURANCE` ¦ MSC login perf ¦ Manual ¦ Manual only ¦ Same ¦
¦ `UNITE-TB-REFRESH` ¦ V2 testbed refresh ¦ On demand ¦ Environment prep ¦ `unite/bin/build.xml` ¦
¦ `ASTRO-TB-REFRESH` ¦ ASTRO testbed ¦ On demand ¦ Environment prep ¦ `astro/bin/build.xml` ¦
¦ V2 UI regression (implicit) ¦ V2 Unite ¦ **Not verified** ¦ **TBD** ¦ Ant targets exist; job name not in repo ¦
**Historical note:** Demand planning (Apr 2026) cited ~779+ combined V2+V3 nightly test cases — **not verified as current pass rate or Jenkins job scope** in this assessment.
---
## Gate classification summary
¦ Classification ¦ Examples ¦
¦----------------¦----------¦
¦ **Hard gate — scheduled regression** ¦ V3 GitLab nightly; metadataweb Stage1 nightly (fail job on error) ¦
¦ **Deployment validation** ¦ GHA Mobile 2 Dashboard slice (external) ¦
¦ **Hard gate — build/deploy** ¦ UniteMSC service pipelines; accountowner Angular build ¦
¦ **Soft / manual** ¦ Stage5 smoke (manual GitLab); MSC perf Jenkins; V2 Ant targets ¦

## Jira-qTest Traceability
gap_id | area | severity | remediation | owner
TQ-01 | Duplicate qTest cases | Medium | Deduplicate and archive obsolete | QA Governance
TQ-02 | Missing Jira links | High | Link scoped stories to qTest cases | BA + QA
TQ-03 | Missing automation_id in repos | High | Publish standard; pilot Mobile 2 | QA Automation
TQ-04 | Tests marked automated without repo mapping | High | Reconciliation collector | QA Automation
TQ-05 | Stale execution history | Medium | Freshness SLA + weekly collector | QA Governance

## Actions and Owners
ID | action | owner | dependency | priority | complexity | target_horizon | acceptance_criteria | evidence | status
CI-001 | Publish repository code-coverage gate matrix | QA Automation | Repo scan complete | P0 | Low | 0-30 days | CSV covers all UniteMSC + QA repos with status labels | repository-code-coverage-gate-matrix.csv | Complete
CI-002 | Deliver Michael Blake final response | QA Automation | Matrix + register | P0 | Low | 0-30 days | Answers all 6 leadership questions; 300-500 words | michael-blake-final-response.md | Complete
CI-003 | Provision read-only GitLab PAT | IT/DevOps | Security approval | P0 | Low | 0-30 days | glab api user returns 200; pipeline collector runs | integration-capability-matrix.csv Blocked | Open
CI-004 | Provision read-only qTest API token | IT/QA Admin | Security approval | P0 | Medium | 0-30 days | QTEST env vars set; test case export succeeds | integration-capability-matrix.csv | Open
CI-005 | Provision read-only Jira API access | IT/QA Admin | Security approval | P0 | Medium | 0-30 days | Jira collector returns scoped stories | jira-scope-assessment.md | Open
CI-006 | Extend Python coverage register collector | QA Automation | CI-003 CI-004 CI-005 | P0 | Medium | 0-30 days | Weekly JSON snapshot; no manual CSV edits | tools/generate_coverage_intelligence_assessment.py | Open
CI-007 | Implement JaCoCo coverage-delta pilot script | QA Automation | DevOps pipeline MR | P0 | Medium | 0-30 days | Script compares branch vs main XML on sample MR | code-coverage-gate-implementation-plan.md | Open
CI-008 | Add JaCoCo XML artifact to unite-mobile2 MR pipeline | DevOps | CI-007 script | P0 | Medium | 0-30 days | MR pipeline publishes jacoco.xml artifact | unite-mobile2/.gitlab-ci.yml | Open
CI-009 | Wire Mobile 2 API GitLab nightly QA-1405 | DevOps + QA | Secure files QA-1405 | P0 | Medium | 0-30 days | Green scheduled job; JUnit artifacts archived | api-test-automation/.gitlab-ci.yml gap E-009 | Open
CI-010 | Refresh Mobile 2 master execution sign-off | QA Automation | CI-009 optional | P1 | Low | 0-30 days | New run post-cee0de9; M-M2-EXEC updated | 17-mobile2-api-automation-signoff.md Stale | Open
CI-011 | Define automation_id traceability standard | QA Automation | Team agreement | P1 | Low | 0-30 days | Published standard; 10+ M2 tests linked | jira-qtest-ci-harmonization-plan.md | Open
CI-012 | qTest read-only collector MVP | QA Automation | CI-004 | P1 | Medium | 31-60 days | qtest-snapshot.json weekly | qtest-readiness-assessment.md | Open
CI-013 | Jira scope collector MVP | QA Automation | CI-005 | P1 | Medium | 31-60 days | jira-scope-snapshot.json weekly | jira-scope-assessment.md | Open
CI-014 | GitLab live pipeline execution collector | QA Automation | CI-003 | P1 | Medium | 31-60 days | execution-snapshot.json with last-run per job | pipeline-job-inventory.csv | Open
CI-015 | GitHub Actions collector | QA Automation | gh CLI + token | P2 | Medium | 31-60 days | gha-execution-snapshot.json for M2 workflow | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | Open
CI-016 | Jenkins collector for V2/perf jobs | QA Automation | Jenkins API access | P2 | Medium | 31-60 days | jenkins-execution-snapshot.json | universal-platform-coverage Jenkins exports | Open
CI-017 | Reconciliation engine v2 with contradiction detection | QA Automation | CI-012 CI-013 CI-014 | P1 | High | 31-60 days | cross-system-traceability.csv + data-conflicts.csv | 07-reconciliation/reconciliation-summary.md | Open
CI-018 | qTest data-quality remediation sprint | QA Governance + BA | CI-012 | P1 | Medium | 31-60 days | ≥5 DQ findings closed; row IDs exported | qtest-data-quality-summary.csv | Open
CI-019 | Configure coverage-delta required status check on pilot repo | DevOps | CI-008 Phase 2 | P0 | Medium | 61-90 days | MR blocked when check fails; bypass group works | code-coverage-gate-decision-brief.md | Open
CI-020 | Establish controlled bypass process and exception register | QA Governance + DevOps | Leadership approval | P0 | Low | 61-90 days | Monthly exception CSV; waiver fields mandatory | ci-gate-strategy.md | Open
CI-021 | Define freshness SLA for register metrics | QA Governance | Register MVP | P1 | Low | 0-30 days | Published SLA in governance model | data-freshness-and-ownership.md | Open
CI-022 | Leadership reporting automation | QA Automation | CI-006 | P1 | Medium | 61-90 days | Weekly leadership MD from register; no blended % | executive-summary.md | Open
CI-023 | Reconcile unite-financial JaCoCo POM inconsistency | Engineering | None | P2 | Low | 31-60 days | Properties match jacoco-check minimums | unite-financial/pom.xml | Open
CI-024 | Sonar enablement decision for UniteMSC | DevOps + Security | Architecture review | P2 | High | 61-90 days | RUN_SONARQUBE policy documented | source-code-coverage-assessment.md | Open
CI-025 | Roll out coverage-delta to unite-profile and unite-account | DevOps | CI-019 pilot success | P2 | Medium | 61-90 days | 2 additional repos on Phase 2 | repository-code-coverage-gate-matrix.csv | Open
CI-026 | Clone and audit GHA Mobile2 workflow repository | QA Automation | Repo access | P2 | Low | 31-60 days | Workflow YAML in evidence register | E-011 workflow not in clone | Open
CI-027 | Verify Jenkins V2 UI regression job scope | QA Automation | Jenkins access | P2 | Medium | 31-60 days | Job name schedule documented in register | ci-gate-assessment.md TBD | Open
CI-028 | Approve domain-specific denominators | Leadership | Program review | P0 | Low | 0-30 days | Signed metric definition A-E | coverage-metric-definition.md | Open

## 30-60-90 Roadmap
# Coverage Intelligence — 30 / 60 / 90 Day Plan
**As of:** 2026-07-21
**Owner:** QA Automation (register) + DevOps (gates) + Leadership (denominators/exceptions)
**Metric authority:** `government-savings-automation-assessment/03-analysis/verified-metrics-register.csv`
---
## Executive summary
Government Savings has meaningful automation and strong GitLab merge hygiene, but **coverage intelligence is platform-specific and not yet harmonized**. This plan delivers a read-only central register, live CI collectors, and a phased code-coverage-delta pilot — **without** a single blended percentage or a large new application.
---
## Days 0–30: Foundation and pilot start
### Goals
- Answer leadership questions with verified, dated metrics
- Unblock API access
- Start JaCoCo delta pilot (informational)
- Schedule Mobile 2 API nightly
### Deliverables
¦ # ¦ Deliverable ¦ Owner ¦ Evidence of done ¦
¦---¦-------------¦-------¦------------------¦
¦ 1 ¦ Michael Blake final response + decision brief ¦ QA Automation ¦ Published MD files ¦
¦ 2 ¦ Repository control matrix ¦ QA Automation ¦ `repository-code-coverage-gate-matrix.csv` ¦
¦ 3 ¦ Leadership-approved metric definitions A–E ¦ Program + QA ¦ Signed governance doc ¦
¦ 4 ¦ Read-only credentials (GitLab, qTest, Jira) ¦ IT ¦ Connectivity matrix **Available** ¦
¦ 5 ¦ Weekly register automation v1 ¦ QA Automation ¦ Scheduled collector run ¦
¦ 6 ¦ JaCoCo delta script + informational MR output ¦ QA Automation ¦ Sample MR comment ¦
¦ 7 ¦ Mobile 2 GitLab nightly (QA-1405) ¦ DevOps + QA ¦ Green scheduled pipeline ¦
¦ 8 ¦ Freshness SLA published ¦ QA Governance ¦ `data-freshness-and-ownership.md` updated ¦
### Key metrics at day 30
¦ Metric ¦ Current ¦ Target ¦
¦--------¦---------¦--------¦
¦ M-M2-CI (scheduled) ¦ 0% ¦ 100% (1/1 job) ¦
¦ M-M2-EXEC ¦ 88% stale ¦ Refreshed or explicitly dated ¦
¦ Repos with informational coverage delta ¦ 0 ¦ 1 (`unite-mobile2`) ¦
¦ Live API integrations ¦ 0 Available ¦ ≥3 Available ¦
---
## Days 31–60: Reconciliation and execution evidence
### Goals
- Connect Jira, qTest, repos, and GitLab execution
- Pilot traceability identifiers
- Tune coverage thresholds
### Deliverables
¦ # ¦ Deliverable ¦ Owner ¦ Evidence of done ¦
¦---¦-------------¦-------¦------------------¦
¦ 9 ¦ qTest snapshot collector ¦ QA Automation ¦ `qtest-snapshot.json` weekly ¦
¦ 10 ¦ Jira scope collector ¦ QA Automation ¦ `jira-scope-snapshot.json` weekly ¦
¦ 11 ¦ GitLab execution collector ¦ QA Automation ¦ `execution-snapshot.json` ¦
¦ 12 ¦ `automation_id` pilot (Mobile 2) ¦ QA Automation ¦ ≥10 tests linked ¦
¦ 13 ¦ Reconciliation v2 + contradictions ¦ QA Automation ¦ `data-conflicts.csv` reviewed ¦
¦ 14 ¦ qTest DQ remediation ¦ QA + BA ¦ ≥5 items closed ¦
¦ 15 ¦ Coverage soft-fail on pilot repo ¦ DevOps ¦ Job fails; bypass tested ¦
¦ 16 ¦ GHA workflow repo audit ¦ QA Automation ¦ YAML in evidence register ¦
### Key metrics at day 60
¦ Metric ¦ Target ¦
¦--------¦--------¦
¦ Critical scenario Jira↔qTest↔repo chain ¦ ≥30% ¦
¦ Repo → pipeline mapping ¦ ≥80% ¦
¦ Contradictions flagged automatically ¦ Yes ¦
¦ Pilot repo soft gate ¦ Operational ¦
---
## Days 61–90: Governance and selective gates
### Goals
- Required coverage check on pilot repo
- Leadership reporting automation
- Exception audit process live
### Deliverables
¦ # ¦ Deliverable ¦ Owner ¦ Evidence of done ¦
¦---¦-------------¦-------¦------------------¦
¦ 17 ¦ Required MR status check (pilot) ¦ DevOps ¦ Merge blocked on coverage fail ¦
¦ 18 ¦ Exception register (monthly) ¦ QA Governance ¦ First published CSV ¦
¦ 19 ¦ Rollout to 2 additional services ¦ DevOps ¦ profile + account ¦
¦ 20 ¦ Jenkins + GHA collectors ¦ QA Automation ¦ Execution snapshots ¦
¦ 21 ¦ Traceability soft gate on QA MRs ¦ QA + Dev ¦ MR template enforced ¦
¦ 22 ¦ Quarterly leadership register cadence ¦ QA Lead ¦ First quarterly report ¦
¦ 23 ¦ Sonar enablement go/no-go ¦ Architecture ¦ Policy memo ¦
### Key metrics at day 90

## Evidence Register
evidence_id | claim | source_type | reference | as_of | confidence | owner
E-M2-IMPL | Mobile 2 24/24 automatable endpoints | GitLab repository | https://gitlab.com/ascensus-gs/products/depot/qa-automation/api-test-automation/-/blob/main/mobile/mobile2 @ cee0de9 | 2026-07-21 | High | QA Automation
E-V3-CI | Modern Unite GitLab nightly active | GitLab CI YAML | https://gitlab.com/ascensus-gs/products/depot/qa-automation/prime-test-automation/-/blob/main/.gitlab-ci.yml @ 93f8628 | 2026-07-21 | High | QA Automation
E-GHA-M2 | Mobile 2 GitHub QC4 integration validated | SME confirmation | Dashboard vertical slice validated with Chaitanya; Nexus workflow | 2026-07-21 | Medium | QA Automation
E-QA1405 | GitLab nightly pending | Jira | QA-1405; DevOps capacity constraint | 2026-07-21 | High | DevOps

## Exceptions
waiver_id | repository | reason | approver | risk_owner | expiration | status
TEMPLATE | [5 empty] | Template