## Action Backlog
ID | action | owner | dependency | priority | complexity | target_horizon | acceptance_criteria | evidence | status
CI-001 | Publish repository code-coverage gate matrix | QA Automation | Repo scan complete | P0 | Low | 0-30 days | CSV covers all UniteMSC + QA repos with status labels | repository-code-coverage-gate-matrix.csv | Complete
CI-002 | Deliver Michael Blake final response | QA Automation | Matrix + register | P0 | Low | 0-30 days | Answers all 6 leadership questions; 300-500 words | michael-blake-final-response.md | Complete
CI-003 | Provision read-only GitLab PAT | IT/DevOps | Security approval | P0 | Low | 0-30 days | glab api user returns 200; pipeline collector runs | integration-capability-matrix.csv Blocked | Open
CI-004 | Provision read-only qTest API token | IT/QA Admin | Security approval | P0 | Medium | 0-30 days | QTEST env vars set; test case export succeeds | integration-capability-matrix.csv | Open
CI-005 | Provision read-only Jira API access | IT/QA Admin | Security approval | P0 | Medium | 0-30 days | Jira collector returns scoped stories | jira-scope-assessment.md | Open
CI-006 | Extend Python coverage register collector | QA Automation | CI-003 CI-004 CI-005 | P0 | Medium | 0-30 days | Weekly JSON snapshot; no manual CSV edits | tools/generate_coverage_intelligence_assessment.py | Open
CI-007 | Implement JaCoCo coverage-delta pilot script | QA Automation | DevOps pipeline MR | P0 | Medium | 0-30 days | Script compares branch vs main XML on sample MR | code-coverage-gate-implementation-plan.md | Open
CI-008 | Add JaCoCo XML artifact to unite-mobile2 MR pipeline | DevOps | CI-007 script | P0 | Medium | 0-30 days | MR pipeline publishes jacoco.xml artifact | unite-mobile2/.gitlab-ci.yml | Open
CI-009 | Wire Mobile 2 API GitLab nightly QA-1405 | DevOps + QA | Secure files QA-1405 | P0 | Medium | 0-30 days | Green scheduled job; JUnit artifacts archived | api-test-automation/.gitlab-ci.yml gap E-009 | Open
CI-010 | Refresh Mobile 2 master execution sign-off | QA Automation | CI-009 optional | P1 | Low | 0-30 days | New run post-cee0de9; M-M2-EXEC updated | 17-mobile2-api-automation-signoff.md Stale | Open
CI-011 | Define automation_id traceability standard | QA Automation | Team agreement | P1 | Low | 0-30 days | Published standard; 10+ M2 tests linked | jira-qtest-ci-harmonization-plan.md | Open
CI-012 | qTest read-only collector MVP | QA Automation | CI-004 | P1 | Medium | 31-60 days | qtest-snapshot.json weekly | qtest-readiness-assessment.md | Open
CI-013 | Jira scope collector MVP | QA Automation | CI-005 | P1 | Medium | 31-60 days | jira-scope-snapshot.json weekly | jira-scope-assessment.md | Open
CI-014 | GitLab live pipeline execution collector | QA Automation | CI-003 | P1 | Medium | 31-60 days | execution-snapshot.json with last-run per job | pipeline-job-inventory.csv | Open
CI-015 | GitHub Actions collector | QA Automation | gh CLI + token | P2 | Medium | 31-60 days | gha-execution-snapshot.json for M2 workflow | 17-MOBILE2-NEXUS-GITHUB-ACTIONS-PIPELINE.md | Open
CI-016 | Jenkins collector for V2/perf jobs | QA Automation | Jenkins API access | P2 | Medium | 31-60 days | jenkins-execution-snapshot.json | universal-platform-coverage Jenkins exports | Open
CI-017 | Reconciliation engine v2 with contradiction detection | QA Automation | CI-012 CI-013 CI-014 | P1 | High | 31-60 days | cross-system-traceability.csv + data-conflicts.csv | 07-reconciliation/reconciliation-summary.md | Open
CI-018 | qTest data-quality remediation sprint | QA Governance + BA | CI-012 | P1 | Medium | 31-60 days | ≥5 DQ findings closed; row IDs exported | qtest-data-quality-summary.csv | Open
CI-019 | Configure coverage-delta required status check on pilot repo | DevOps | CI-008 Phase 2 | P0 | Medium | 61-90 days | MR blocked when check fails; bypass group works | code-coverage-gate-decision-brief.md | Open
CI-020 | Establish controlled bypass process and exception register | QA Governance + DevOps | Leadership approval | P0 | Low | 61-90 days | Monthly exception CSV; waiver fields mandatory | ci-gate-strategy.md | Open
CI-021 | Define freshness SLA for register metrics | QA Governance | Register MVP | P1 | Low | 0-30 days | Published SLA in governance model | data-freshness-and-ownership.md | Open
CI-022 | Leadership reporting automation | QA Automation | CI-006 | P1 | Medium | 61-90 days | Weekly leadership MD from register; no blended % | executive-summary.md | Open
CI-023 | Reconcile unite-financial JaCoCo POM inconsistency | Engineering | None | P2 | Low | 31-60 days | Properties match jacoco-check minimums | unite-financial/pom.xml | Open
CI-024 | Sonar enablement decision for UniteMSC | DevOps + Security | Architecture review | P2 | High | 61-90 days | RUN_SONARQUBE policy documented | source-code-coverage-assessment.md | Open
CI-025 | Roll out coverage-delta to unite-profile and unite-account | DevOps | CI-019 pilot success | P2 | Medium | 61-90 days | 2 additional repos on Phase 2 | repository-code-coverage-gate-matrix.csv | Open
CI-026 | Clone and audit GHA Mobile2 workflow repository | QA Automation | Repo access | P2 | Low | 31-60 days | Workflow YAML in evidence register | E-011 workflow not in clone | Open
CI-027 | Verify Jenkins V2 UI regression job scope | QA Automation | Jenkins access | P2 | Medium | 31-60 days | Job name schedule documented in register | ci-gate-assessment.md TBD | Open
CI-028 | Approve domain-specific denominators | Leadership | Program review | P0 | Low | 0-30 days | Signed metric definition A-E | coverage-metric-definition.md | Open