# Government Savings

Coverage-Delta Gate — Technical Implementation Plan

Prepared by: Swapnil Patil
QA Automation & Quality Program Lead, Government Savings

Assessment Date: July 21, 2026
Version: 1.0
Classification: Confidential — Internal Use

# Code Coverage Gate Implementation Plan

## Code Coverage Gate — Technical Implementation Plan

**As of:** 2026-07-21

**Scope:** Government Savings application repositories (UniteMSC primary)

**Principle:** Phased, repository-specific; retain existing merge controls

---

## 1. Objectives

1. Measure **application source-code coverage (metric A)** on every MR/PR.

2. Prevent **material regression** versus `main` and enforce **changed-code** thresholds.

3. Publish a **required MR status check** without weakening existing Snyk, approval, or discussion rules.

4. Provide **auditable exceptions** via a restricted bypass group.

5. Keep **business automation coverage (metric B)** in the separate coverage register.

---

## 2. Current baseline (revalidated)

| Finding | Evidence | Status |

|---------|----------|--------|

| JaCoCo present on 13 UniteMSC Java services | `pom.xml` scans | Verified from repository code |

| SonarQube disabled | `RUN_SONARQUBE: false` | Verified from repository code |

| Static `jacoco-check` thresholds vary 0%–90% | POM grep | Verified from repository code |

| No `coverage:` regex or `coverage_report` in QA CI YAML | `.gitlab-ci.yml` | Verified absent |

| No branch-vs-main comparison script | Repo scan | Verified absent |

| GitLab protected-branch settings | Org standard | Pending live verification (API 401) |

---

## 3. Recommended gate design

## Selected model: Option 2 + Option 3 (phased)

| Check | Phase 1 | Phase 2 | Phase 3 |

|-------|---------|---------|---------|

| Unit/integration tests on MR | Yes | Yes | Yes |

| JaCoCo XML artifact | Yes | Yes | Yes |

| Changed-code coverage | Report only | Warn | Fail |

| Overall vs `main` regression | Report only | Fail >2pp drop | Fail >1pp drop |

| MR status check | Optional | Recommended | **Required** |

| Merge block | No | Soft (override) | Yes |

| Exception audit | N/A | Pilot | Monthly register |

**Repository-specific thresholds (examples):**

| Repository | Changed-code min | Regression tolerance |

|------------|------------------|----------------------|

| `unite-mobile2` | 80% lines | 1pp overall |

| `unite-profile` | 80% lines | 1pp overall |

| `unite-account` | 50% lines | 2pp overall |

| Legacy 0% services | 60% changed-code only | 0pp drop first 90 days |

---

## 4. Architecture

```

MR opened

→ CI: mvn verify (existing test stage)

→ JaCoCo: target/site/jacoco/jacoco.xml

→ Fetch main baseline artifact (last green main pipeline)

→ Python/GitLab CI script: compare + changed-code diff

→ Publish GitLab coverage + MR note + pass/fail job

→ If fail: block merge (Phase 3) unless exception group approves

→ Log exception to coverage-exception-register.csv

```

**Baseline storage:** GitLab job artifact from `main` (30-day retention minimum) or object storage via DevOps template.

---

## 5. Implementation phases

## Phase 1 — Informational (days 0–30)

| # | Task | Owner | Deliverable |

|---|------|-------|-------------|

| 1.1 | Select pilot repo (`unite-mobile2`) | QA + DevOps | Decision recorded |

| 1.2 | Add JaCoCo XML artifact to MR pipeline | DevOps | Pipeline MR |

| 1.3 | Implement `compare_jacoco.py` (read-only) | QA Automation | Script in KB tools |

| 1.4 | MR comment with delta summary | QA Automation | Sample MR output |

| 1.5 | Document thresholds in decision brief | QA Lead | Approved thresholds |

## Phase 2 — Soft gate (days 31–60)

| # | Task | Owner | Deliverable |

|---|------|-------|-------------|

| 2.1 | Fail job on threshold breach | DevOps | CI job `coverage-delta-check` |

| 2.2 | Configure exception group in GitLab | DevOps | Group + approval rule |

| 2.3 | Exception form fields (reason, expiry) | QA Governance | Template |

| 2.4 | Extend to `unite-profile`, `unite-account` | DevOps | 2 additional repos |

| 2.5 | Enable Sonar pilot (optional) | DevOps | `RUN_SONARQUBE: true` on 1 service |

## Phase 3 — Required merge check (days 61–90)

| # | Task | Owner | Deliverable |

|---|------|-------|-------------|

| 3.1 | Add `coverage-delta-check` to protected-branch required statuses | DevOps | Settings change |

| 3.2 | Rollout remaining UniteMSC services | DevOps | Phased by risk tier |

| 3.3 | Monthly exception register report | QA Automation | Leadership CSV |

| 3.4 | Reconcile `unite-financial` POM inconsistency | Engineering | Fixed jacoco-check |

## Phase 4 — Monitoring (ongoing)

- Trend dashboard in coverage register

- Quarterly threshold review

- Contradiction detection vs Sonar (if enabled)

---

## 6. Tooling

| Component | Tool | Notes |

|-----------|------|-------|

| Coverage generation | JaCoCo Maven plugin | Already in POMs |

| Delta comparison | Python (`xml.etree`, `diff`) | Extend `live_validation_build.py` pattern |

| MR integration | GitLab CI + `glab`/`curl` API | Requires valid PAT |

| Changed-code scope | `git diff origin/main...HEAD` | Standard |

| Reporting | CSV register + leadership MD | No new web app |

| Optional | SonarQube changed-code | After `RUN_SONARQUBE` policy |

---

## 7. What QA Automation delivers directly

- `compare_jacoco.py` and register integration

- Pilot validation on sample MRs

- Repository matrix maintenance

- Leadership reports and exception register

- Traceability standards for QA repos (metric B, separate track)

---

## 8. What requires DevOps / Engineering

- Shared pipeline template in `ascensus-gs/shared/gitlab/templates`

- Protected-branch required status configuration

- Baseline artifact retention policy

- Bypass group membership and GitLab approval rules

- Sonar enablement and credentials

- Production secrets for CI

---

## 9. Success criteria

| Criterion | Target |

|-----------|--------|

| Pilot repo MR shows coverage delta | By day 30 |

| Documented exception with audit trail | By day 45 |

| Required check on pilot repo | By day 90 |

| Zero conflation of metrics A and B in leadership reports | Ongoing |

| GitLab API connectivity | Unblocked |

---

## 10. Out of scope (initial 90 days)

- Single GS-wide coverage percentage

- Blocking merge on full business regression suite

- qTest/Jira writes from automation

- Custom web application

- Identical threshold for all 14 services

---

*Related: `repository-code-coverage-gate-matrix.csv`, `code-coverage-gate-decision-brief.md`, `coverage-intelligence-assessment/08-solution/jira-qtest-ci-harmonization-plan.md`*