## Slide 1
Unite MSC Automation Program
Weekly Leadership Update · July 17, 2026
QA AUTOMATION
AMSQUAD
Prepared for: Rajiv/Rajib, Henry, Kevin

## Slide 2
Executive Summary
From fragmented legacy coverage to reusable canonical automation
Mobile 2 API
Baseline functionally complete — 88% endpoint coverage verified. Ready for leadership sign-off pending evidence refresh.
Mobile 1 API
Active sprint focus. Authentication foundation complete; business endpoint automation now underway.
Performance
Foundation live on MSC Jenkins. Non-IDP login flow complete; IDP and nightly schedule expanding.
Pipeline
GHA deployment validation slice complete. GitLab nightly regression job pending DevOps story approval.
V2/V3 UI
Stable nightly regression running. Daily triage cadence established and maintained by the team.

## Slide 3
Program Metrics Snapshot
Readiness by workstream — as of July 17, 2026, in Percentile
Note: Mobile 2 and Mobile 1 percentages reflect endpoint automation coverage. Pipeline, Performance, and V2/V3 UI reflect qualitative program readiness assessments.

## Slide 4
Mobile 2 Endpoint Coverage
88% Verified
As of 2026-07-14 — the formal validation checkpoint.
Coverage is not claimed at 100%. Three endpoints remain excluded or in-gap pending team disposition.
Projected coverage increases after post-07/14 merges are incorporated. A refreshed validation run is required before final sign-off.

## Slide 5
Mobile 2 Sign-Off Path
Baseline functionally complete — pending evidence refresh
✅ COMPLETED
Canonical TestNG Migration
Full migration from legacy framework to reusable canonical TestNG structure complete.
OKD + NMD Environment Support
Test suites validated against both OKD and NMD deployment targets.
Dynamic SQL Auth + Master Suites
Dynamic authentication via SQL and master suite orchestration fully implemented.
🔲 OPEN ITEMS
Final MR Merge
Outstanding merge request must be closed before evidence snapshot is refreshed.
QC4 + Stage 1 Execution Run
Full suite execution required on QC4 and Stage 1 environments to confirm stability.
GitLab Nightly Job Creation
DevOps story approval required to establish the scheduled regression job in GitLab.

## Slide 6
Mobile 1 — Active Sprint Focus
1 of 27 endpoints automated to date
Authentication Foundation Complete
The non-IDP authentication baseline has been established, enabling systematic business endpoint automation to begin this sprint. IDP compatibility work is scoped for the following sprint.
1
This Sprint (26.11)
Mobile 1 Non-IDP baseline — core business endpoint automation
2
Next Sprint (26.12)
Mobile 1 IDP compatibility + suite hardening and stabilization

## Slide 7
CI/CD Pipeline Workflow
GitHub Actions deployment validation is distinct from GitLab nightly regression
GitHub Actions
Nexus Archive
Maven Build
Source Code
✅ COMPLETE
GitHub Actions Dashboard — Deployment validation slice confirmed live and operational.
🔶 IN PROGRESS
Module Suites — Suite wiring to GHA pipeline actively being configured and tested.
⬜ PENDING
GitLab Nightly — Scheduled regression job requires DevOps story creation and approval.

## Slide 8
Performance Regression Status
MSC Jenkins Job
✅ Available — Performance regression job provisioned on MSC Jenkins. Foundation infrastructure is live.
Non-IDP Login → Dashboard
✅ Complete — End-to-end non-IDP login through dashboard flow validated and passing.
IDP MSC Login
🔶 In Progress — IDP-based login flow under active development. Blocked on clean manual validation baseline.
Nightly Schedule
⬜ Pending — Nightly execution will be enabled after manual validations pass cleanly and consistently.
Next flows in queue: Contribution, Banks, Activity, Mobile 1 — to be sequenced after IDP flow stabilization.

## Slide 9
Risks & Dependencies
RAG Status — July 17, 2026
Risk / Dependency
Severity
Impact & Mitigation
GitLab Nightly Not Created
🔴 High
Blocks continuous regression signal for Mobile 2 sign-off. Requires DevOps story approval this sprint.
Stage 1 / Stage 5 / QC2 Test Data
🟡 Medium
Missing or inconsistent test data in environments delays suite execution and sign-off evidence.
Enrollment Encryption / Test-Data Utility
🟡 Medium
Multi-sprint complexity. Dependency on shared utility development cadence outside team control.
Reporting / Admin Load
🟡 Medium
Administrative overhead reducing available engineering sprint capacity. Escalation support requested.
Ad-Hoc Intake (Unstructured)
🟡 Medium
Unplanned requests disrupting sprint commitments. Structured backlog intake enforcement needed.

## Slide 10
Leadership Asks & Sprint Roadmap
Leadership Actions Requested
01
Approve DevOps Story
Authorize GitLab nightly regression job for Mobile 2 — critical for sign-off evidence.
02
Confirm Mobile 2 Sign-Off
Review and approve sign-off after refreshed evidence run is submitted by the team.
03
Confirm Mobile 1 Priority
Affirm sprint commitment to Mobile 1 non-IDP baseline this sprint (26.11).
04
Support Pipeline & Environments
Ensure environment readiness and DevOps alignment across Stage 1, QC4, and GitLab.
05
Enforce Backlog Intake + Protect Capacity
Structured intake for all ad-hoc requests. Support 30–40% capacity protection from BA/Scrum/admin load.
Sprint Roadmap
1
Sprint 26.11
Mobile 2 sign-off · Mobile 1 non-IDP baseline · Pipeline GHA module wiring
2
Sprint 26.12
Mobile 1 IDP compatibility · Suite hardening · GitLab nightly regression live
3
Horizon
Enrollment API — multi-sprint effort · Performance full flow coverage